## Test Summary
Dematic Sorter Testing
Test Name | Test Purpose | Comment | DC Team | Head Office Team | Vendor Team | Worksheet Reference | Not executed | In progress | Pass | Fail | Pending | Retest | Total
Pre-Work | Preparation for below tests prior to test day |  | DC Operations | Support |  | Pre-Work
Printer test of 2D barcodes | Testing printing of 1WMS generated 2D barcodes |  | DC Operations |  |  | Printers | 3 | [5 empty] | 3
Sorter Standard | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | Sorter Standard | 7 | [5 empty] | 7
Sorter Volume Rates | Volume testing of quality 2D labels |  | DC Ops, Sorter Manager | Support | Support | Sorter Volume | 2 | [5 empty] | 2
Sorter Duplicate label tests | Heirarchy testing of duplicates of 1D and 2D labels | Test at one site only | DC Ops, Sorter Manager | Support | Support | Sorter Dups | 7 | [5 empty] | 7
Sorter Bad Label Limit tests | Test limits for processing bad labels | Test at one site only | DC Ops, Sorter Manager | Support | Support | Sorter Bad Label | 26 | [5 empty] | 26
Sorter Bad Label Comparison tests | Comparison of performance of 2D and 1D 92/93 labels | Test at one site only | DC Ops, Sorter Manager | Support | Support | Sorter Bad Compare | 26 | [5 empty] | 26
[6 empty] | Total | 71 | 0 | 0 | 0 | 0 | 0 | 71
[6 empty] | Percentage | 100% | 0% | 0% | 0% | 0% | 0%

## Pre-Work
Test Sheet | Product Required | Quantity | Comment | Label Source
Printers | 92/93 UNRES Pick and Pack in 351 | 3 |  | DC
Sorter Standard | 91 Labelled sortable medium sized carton | 5 | Ensure that label messages are inducted to sort director | DC
Sorter Standard | 00 Labelled sortable medium sized carton | 5 | Ensure that label messages are inducted to sort director | DC
Sorter Standard | 1D 92/93 Labelled sortable medium sized carton | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock
Sorter Standard | 2D 92/93 Labelled sortable medium sized carton | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Standard | 2D 92/93 Labelled sortable small sized carton | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Standard | 2D 92/93 Labelled sortable large sized carton | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Standard | 2D 92/93 Labelled sortable polybag (cardboard backed) | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Volume - Vol_01 | 2D 92/93 Labelled sortable cartons | 1000 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Volume - Vol_02 - 1 | 2D 92/93 Labelled sortable cartons | 1000 | Mix with below, ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Volume - Vol_02 - 2 | 1D 92/93 Labelled sortable cartons | 1000 | Mix with above, ensure messages are inducted | DC Overseas Stock
Below is only required at the first Australian site used for testing
Sorter Dups | 2 x2D 92/93 Labelled sorter cartons | 1 | 2 of same label applied. Inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Dups | 92/93 Labelled carton + 2D label | 1 | Leave 1D label and apply same as 2D on another side. Inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Dups | Replace 92/93 label with 2D + add 91 label | 1 | PnP genuine 92/93 requiring 91 labels. Both inducted i.e another pick with 92/93 label required | Replace 92/93 with 2D; Add 91 Label - DC. CBX Generated for 2D for that stock
Sorter Dups | Local 00 labelled stock + 2D label | 1 | Both inducted. 2D label can be random i.e. not for this stock. | Standard 00 labelled stock, PDF Generated 2D label for other stock from CBX
Sorter Dups | Overseas stock with other 00 barcode + 2D label | 1 | 00 barcode not SSCC. Inducted 92/93. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Dups | 1D 92/93 Labelled carton + 2D label | 1 | 2D label not for this stock, applied on another side. Both inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Dups | 2 x 2D 92/93 Labelled carton. | 1 | 1 x 2D for stock, 1 x 2D for other stock. Both inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for stock and other stock.
Sorter Bad Label | 2D 92/93 labelled cartons | 30 | Prepare per test cases, and induct, requires packing tape too. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Bad Compare | 2D 92/93 labelled cartons - same position as below | 30 | Prepare per test cases, and induct, requires packing tape too. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Sorter Bad Compare | 1D 92/93 labelled cartons - same position as above | 30 | Prepare per test cases, and induct, requires packing tape too. These are twins of the 2D labelled stock, and must be prepared in exactly the same way as the 2D labelled stock for comparison | DC Overseas Stock for same products as 2D labelled stock.

## Printers
Test Name: | Printer Test of 2D barcodes | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Print_1 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Printronix printer. | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 2D Label prints
Print_2 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Intermec PC43D printer. | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 2D Label prints
Print_3 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Intermec PB50 printer. | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 2D Label prints
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Go to option 351 | DC Operator | Enters Pick Management |  |  |  | Enters Pick Management
2 | Enter option 7 and find UNRES stock with CC status | DC Operator | Enters Pick Management - SCMs |  |  |  | Enters Pick Management - SCMs
3 | Use option 9=Re-Print | DC Operator | Verify that label is printed from the approprate printer. Validate that the label is a 2D label |  |  |  | 2D label printed

## Sorter Standard
Test Name: | Sorter Standard | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Sort_01 | Sort a 91 SSCC labelled medium carton product Place 5 items with 91 SSCCs on the sorter. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_02 | Sort a 00 SSCC labelled medium carton product Place 5 items with 00 SSCCs on the sorter. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_03 | Sort a 1D 92/93 SSCC labelled medium carton product Place 5 items with 92/93 SSCCs on the sorter. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_04 | Sort a 2D 92/93 SSCC labelled medium carton product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_05 | Sort a 2D 92/93 SSCC labelled small carton product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_06 | Sort a 2D 92/93 SSCC labelled large sortable carton product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_07 | Sort a 2D 92/93 SSCC labelled sortable polybag product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Ensure that product is flipped to sorter (reset after the test) Orientate as follows: 1. Label is facing up | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | SSCC sorts to store lane
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Record product and orientation of the label(s) in this spreadsheet | DC Operator | Use felt pen to number each box according to orientation and/or record the SSCC number. |  |  |  | Product recorded |  |  |  |  | This is so that failed cases can be identified. 1D = Linear barcodes 2D = Square barcodes
2 | Place product on to the induct lane(s) in orientation described in the test. | DC Operator | Product enters the loop in desired orientation |  |  |  | Product enters the loop correctly
3 | Product enters the scanner tunnel | Sorter Manager | Sort Director shows the SSCC, and appropriate 00, 91 and/or 92/93 SSCC is displayed as scanned. |  |  |  | Product scans successfully |  |  |  |  | Products in all orientations need to scan successfully for the test to pass.
4 | Product sorts to the appropriate lane for the store | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director |  |  |  | Product sorts to the correct store lane
5 | Verify sort in option 36 | DC Operator | Option 36 shows the SSCC |  |  |  | SSCC is shown as sorted ok or shows the reject reason |  |  |  |  | Validates that the SSCC information is returned to 1WMS.
6 | Use Reject Enquiry function to scan the SSCC | DC Operator | Reject Enquiry shows that product sorted to the store, or shows reason for reject (can verify in SSCC Enquiry too). |  |  |  | Reject Enquiry show OK for store lanes, or reject reason |  |  |  |  | Validates that Dematic Sorter Reporting server has received the correct SSCC information.

## Sorter Volume
Test Name: | Sorter Volume Rates | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Vol_01 | Process 1000 2D labelled cartons | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1000 | As Below | 99.9% sort to store lanes
Vol_02 | Process 1000 mixed 1D and 2D labelled cartons 50% of the cartons should be relabelled with 2D labels | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2000 | As Below | 99.9% of 2D labelled cartons sort to store lanes
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare 1000 cartons with labels as required by the test | DC Operator/ HO Support | 1000 cartons prepared for the test with labels applied Product data is inducted to the sorter |  |  |  | 1000 cartons per test with 2D labels prepared |  |  |  |  | Ensure that all product it is sortable and has fresh messages on the sorter.
2 | Place product on to the induct lane(s) with all barcodes in sortable positions (i.e. not facing downwards) | DC Operator | Use all induct lanes Verify that all cartons have barcodes in scannable positions |  |  |  | Around 250 cartons per lane. All cartons in scannable orientations
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC, and appropriate 00, 91 and/or 92/93 SSCC is displayed as scanned. |  |  |  | Product scans successfully
4 | Product sorts to the appropriate lane for the store | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director |  |  |  | Product sorts to the correct store lane
5 | Verify sort in option 36 and extract data | HO Support | Option 36 shows the SSCC Extract sorter data and verify all sorted ok. |  |  |  | SSCC is shown as sorted ok |  |  |  |  | Check for any rejects, and check causes. Test fails if there are 2D barcode read failures when scanned (excluding shadowing, priority conflict or other rejects not due to a bad read of the barcode)

## Sorter Dups
Test Name: | Sorter Priority label tests | [These tests only need to be done at the first Australian site] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Dup_01 | Process a carton with two 92/93 2D SSCC labels that have the same product and SSCC details | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Dup_02 | Process a carton with one 1D 92/93 SSCC label and one 92/93 2D SSCC label that have the same product and SSCC details | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Dup_03 | Process a carton with a 91 label and a 2D 92/93 SSCC label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane shown on 91 label
Dup_04 | Process a carton with a sortable 00 label known to the sorter and a 2D 92/93 label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton rejects with priority conflict (local product should not sort with overseas label)
Dup_05 | Process a carton with a 00 description (non-SSCC) barcode and a 2D 92/93 label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane based on the 92/93 label
Dup_06 | Process a carton with a 1D 92/93 SSCC and a 2D 92/93 with different products encoded in the labels (different 92). | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton rejects with a priority conflict.
Dup_07 | Process a carton with two 2D SSCC labels that have different products encoded (different 92 SSCCs). One 2D label should be for the product in the box. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton rejects with a priority conflict.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare cartons with labels as identified in the test | DC Operator/ HO Support | Labels are placed on the cartons |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate
2 | Place product for test on to the induction lane(s) for the sorter with all barcodes in scannable positions | DC Operator | Barcode labels can be scanned by the sorter |  |  |  | All labels are in scannable positions
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC, and appropriate 00, 91 and/or 92/93 SSCC is displayed as scanned. |  |  |  | Product scans successfully
4 | Product sorts to the appropriate lane for the store or rejects depending on the test. | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director or to the reject lane. Validate that rejects are expected. |  |  |  | Product sorts to the correct store lane or reject lane. Only expected rejects sort to the reject lane.
5 | Verify sort in option 36 and validate rejects | HO Support | Option 36 shows the SSCC Validate rejected products |  |  |  | SSCC is shown in option 36. Only expected rejects are rejected.
6 | Verify reject cause at reject lane | DC Operator | Use Reject Enquiry to scan rejected cartons to determine the cause of the reject |  |  |  | SSCC scans ok. Reject cause is per the test expection (where appropriate).
7 | Black out incorrect label for Priority conflicts and re-sort the carton | DC Operator | Validate that carton sorts ok and does not return to the reject lane. |  |  |  | Remaining label scans ok Product sorts to a store lane.

## Sorter Bad Label
Test Name: | Sorter Bad Label Limit tests | [These tests only need to be done at the first Australian site] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Bad_01 | Label Placement Edge 1 Process a carton with a 92/93 2D label placed with the full label at the edge of the carton | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_02 | Label Placement Edge 2 Process a carton with a 92/93 2D label placed with the label wrapped over the edge of the carton, but all of barcode on one side of the carton | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_03 | Label Placement Edge 3 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped vertically over the edge of the carton | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_04 | Label Placement Edge 4 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped horizontally over the edge of the carton | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_05 | Label Placement Edge 5 Process a carton with a 92/93 2D label placed with the label with 20% of barcode wrapped diagonally over the edge of the carton | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_06 | Label Placement Edge 6 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped diagonally over the edge of the carton | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_07 | Label Placement crease Process a carton with a 92/93 2D label placed over the centre crease where the box opens (3 cartons with different orientations over the centre crease - ensure that crease is visible in the label) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 3 | As Below | Carton sorts to a store lane
Bad_08 | Carton corrugations Process a 92/93 2D label on corrugated box. Ensure that wrinkles on the box go through the barcode on the label. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_09 | Crushed carton With a test box, place a 92/93 2D label inducted to the system. Crush the test box such that the label is wrinkles but still readable by the eye, and sort. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane NB: remove carton and have IT delete the MHS record.
Bad_10 | Tear 1 Tear a corner of the barcode off a 92/93 2D label and place on a carton and sort | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_11 | Tear 2 Tear vertically through 1/3rd of the barcode on a 92/93 2D label and place on a carton and sort | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_12 | Tear 3 Tear vertically through 50% of the barcode on a 92/93 2D label and place on a carton and sort | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort to store. (depends if all four squares are damaged)
Bad_13 | Tear 4 Tear horizontally through 50% of the barcode on a 92/93 2D label and place on a carton and sort | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort to store. (depends if all four squares are damaged)
Bad_14 | Tear 5 Tear diagonally through 50% of the barcode on a 92/93 2D label and place on a carton and sort | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort to store. (depends if all four squares are damaged)
Bad_15 | Poor Print Quality Print a 2D 92/93 label on a printer with poor print quality (unclean or old head) such that some lines print through the barcode and place on a carton and sort | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort to store. (depends if all four squares are damaged)
Bad_16 | Clear tape 1 Process a 2D 92/93 label on a carton where a clear tape obscures one corner of the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_17 | Clear tape 2 Process a 2D 92/93 label on a carton where a clear tape obscures 50% of the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_18 | Clear tape 3 Process a 2D 92/93 label on a carton where a clear tape covers the entire barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort depending on reflections from the tape during the scan.
Bad_19 | Kmart tape 1 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 1/4 of the barcode. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_20 | Kmart tape 2 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 50% of the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_21 | Packing tape 1 Process a 2D 92/93 label on a carton where brown packing tape covers 1/3 of the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_22 | Packing tape 2 Process a 2D 92/93 label on a carton where brown packing tape covers 50% of the barcode vertically, diagonally, horizontally (3 cartons) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 3 | As Below | Carton may or may not sort to store. (depends if all four squares are partially covered)
Bad_23 | Scuff 1 Place 2D 92/93 label on a carton and lightly scuff the label by dragging the carton with label face down for one metre. Process on sorter | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
Bad_24 | Scuff 2 Place 2D 92/93 label on a carton and moderately scuff the label by dragging the carton with label face down for one metre and back with small pressure on top of box. Process on sorter | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort to store. (depends if all four squares are partially damaged)
Bad_25 | Scuff 3 Place 2D 92/93 label on a carton and heavily scuff the label by dragging the carton with label face down for one metre and back with strong pressure on top of box to grind the label. Process on sorter | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton may or may not sort to store. (depends if all four squares are partially damaged)
Bad_26 | Offset print Place 2D 92/93 label on a carton where the barcode is printed at the very edge of the label Process on sorter | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane
30
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare cartons with labels as identified in the test | DC Operator/ HO Support | Labels are placed on the cartons as appropriate for the test Photo each carton for the test. |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate Photos should be sent to Head Office (John Herbert) after the test along with the results
2 | Place product for test on to the induction lane(s) for the sorter with all barcodes in scannable positions | DC Operator | Barcode labels can be scanned by the sorter |  |  |  | All labels are in scannable positions
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC or shows bad or no read. |  |  |  | Product scans successfully or cannot scan
4 | Product sorts to the appropriate lane for the store or rejects depending on the test. | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director or to the reject lane. Validate that rejects are expected. |  |  |  | Product sorts to the correct store lane or reject lane. Only expected rejects sort to the reject lane. |  |  |  |  | For some tests, the condition of the label will reach a limit where it cannot be scanned.
5 | Count successes and failures | Sorter Manager | Record count of successes and failures Identify SSCC No of failures and note associated picture. |  |  |  | Successes and failures recorded and counted Picture documents the test
6 | Verify sort in option 36 and validate rejects | HO Support | Option 36 shows the SSCC Validate rejected products |  |  |  | SSCC is shown in option 36. Only expected rejects are rejected.
7 | Verify reject cause at reject lane | DC Operator | Use Reject Enquiry to scan rejected cartons to determine the cause of the reject |  |  |  | SSCC scans ok. Reject cause is per the test expection (where appropriate).

## Sorter Bad Compare
Test Name: | Sorter Bad Label Comparison | [These tests only need to be done at the first Australian site] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Comp_01 | Label Placement Edge compare 1 Process a carton with a 92/93 2D label placed with the full label at the edge of the carton. Process a second carton with a 1D 92/93 label placed in the identical position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton sorts to a store lane
Comp_02 | Label Placement Edge compare 2 Process a carton with a 92/93 2D label placed with the label wrapped over the edge of the carton, but all of barcode on one side of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton probably rejects
Comp_03 | Label Placement Edge 3 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped vertically over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_04 | Label Placement Edge 4 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped horizontally over the edge of the carton. Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_05 | Label Placement Edge 5 Process a carton with a 92/93 2D label placed with the label with 20% of barcode wrapped diagonally over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_06 | Label Placement Edge 6 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped diagonally over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_07 | Label Placement crease Process a carton with a 92/93 2D label placed over the centre crease where the box opens (3 cartons with different orientations over the centre crease - ensure that crease is visible in the label) Process a second set of cartons with a 1D 92/93 label placed in the identical position with crease visible on each label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 6 | As Below | 2D Carton sorts to a store lane 1D Carton rejects sometimes
Comp_08 | Carton corrugations Process a 92/93 2D label on corrugated box. Ensure that wrinkles on the box go through the barcode on the label. Process a second carton with a 1D 92/93 label placed in the similar position with wrinkles in the label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject
Comp_09 | Crushed carton With a test box, place a 92/93 2D label inducted to the system. Crush the test box such that the label is wrinkles but still readable by the eye, and sort. Process a second carton with a 1D 92/93 label placed in the identical position and crushed in a similar way | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may sort to a store lane 1D Carton rejects NB: remove the test cartons wherever they go, and have IT delete the MHS records for them.
Comp_10 | Tear 1 Tear a corner of the barcode off a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_11 | Tear 2 Tear vertically through 1/3rd of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_12 | Tear 3 Tear vertically through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton rejects
Comp_13 | Tear 4 Tear horizontally through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton rejects
Comp_14 | Tear 5 Tear diagonally through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton rejects
Comp_15 | Poor Print Quality Print a 2D 92/93 label on a printer with poor print quality (unclean or old head) such that some lines print through the barcode and place on a carton and sort Process a second carton with a 1D 92/93 label placed in the identical position and the label printed on the same printer. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton may or may not reject
Comp_16 | Clear tape 1 Process a 2D 92/93 label on a carton where a clear tape obscures one corner of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject
Comp_17 | Clear tape 2 Process a 2D 92/93 label on a carton where a clear tape obscures 50% of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject
Comp_18 | Clear tape 3 Process a 2D 92/93 label on a carton where a clear tape covers the entire barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort depending on reflections from the tape during the scan. 1D Carton may reject for the same reason.
Comp_19 | Kmart tape 1 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 1/4 of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject
Comp_20 | Kmart tape 2 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 50% of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject
Comp_21 | Packing tape 1 Process a 2D 92/93 label on a carton where brown packing tape covers 1/3 of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
Comp_22 | Packing tape 2 Process a 2D 92/93 label on a carton where brown packing tape covers 50% of the barcode vertically, diagonally, horizontally (3 cartons). Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position.. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 6 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are partially covered) 1D Carton rejects
Comp_23 | Scuff 1 Place 2D 92/93 label on a carton and lightly scuff the label by dragging the carton with label face down for one metre. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may or may not reject
Comp_24 | Scuff 2 Place 2D 92/93 label on a carton and moderately scuff the label by dragging the carton with label face down for one metre and back with small pressure on top of box. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are partially damaged). 1D Carton may or may not reject
Comp_25 | Scuff 3 Place 2D 92/93 label on a carton and heavily scuff the label by dragging the carton with label face down for one metre and back with strong pressure on top of box to grind the label. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are partially damaged). 1D Carton may or may not reject
Comp_26 | Offset print Place 2D 92/93 label on a carton where the barcode is printed at the very edge of the label Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position, and also printed with little/no white space at the end of the 92 label. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects
60
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare cartons with labels as identified in the test. 2D and 1D test cases should be identical | DC Operator/ HO Support | Labels are placed on the cartons as appropriate for the test Photo each carton for the test. |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate Photos should be sent to Head Office (John Herbert) after the test along with the results
2 | Place product for test on to the induction lane(s) for the sorter with all barcodes in scannable positions | DC Operator | Barcode labels can be scanned by the sorter |  |  |  | All labels are in scannable positions
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC or shows bad or no read. |  |  |  | Product scans successfully or cannot scan
4 | Product sorts to the appropriate lane for the store or rejects depending on the test. | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director or to the reject lane. Validate that rejects are expected. |  |  |  | Product sorts to the correct store lane or reject lane. Only expected rejects sort to the reject lane. |  |  |  |  | For some tests, the condition of the label will reach a limit where it cannot be scanned.
5 | Count successes and failures | Sorter Manager | Record count of successes and failures Identify SSCC No of failures and note associated picture. |  |  |  | Successes and failures recorded and counted Picture documents the test
6 | Verify sort in option 36 and validate rejects | HO Support | Option 36 shows the SSCC Validate rejected products |  |  |  | SSCC is shown in option 36. Only expected rejects are rejected.
7 | Verify reject cause at reject lane | DC Operator | Use Reject Enquiry to scan rejected cartons to determine the cause of the reject |  |  |  | SSCC scans ok. Reject cause is per the test expection (where appropriate).
8 | Compare counts of successes and failures between 1D and 2D labels | HO Support | Compare successes and rejects for each label type. |  |  |  | 2D labels perform significantly better than their 1D equivalents. |  |  |  |  | Overall result test fails if 1D labels sort more consistently than the 2D labels. Overall result test fails if 1D labels perform about the same as the 2D labels.

## Cntl Card (hidden)
Test Status
Not executed
In progress
Pass
Fail
Pending
Retest
NA

## Test Plan (hidden)
Test Plan
Nbr of days for SIT | 25
Total Nbr of SIT Test Cases | #REF!
Nbr of Test Cases / Day | #REF!
Nbr | Test Case ID | Day | Work Field for Conditional Formatting
1 | BSCT-Article-01 | #REF! | #REF!
2 | BSCT-Article-02A | #REF! | #REF!
3 | BSCT-Article-02B | #REF! | #REF!
4 | BSCT-Article-03 | #REF! | #REF!
5 | BSCT-Article-04 | #REF! | #REF!
6 | BSCT-Article-05 | #REF! | #REF!
7 | BSCT-Article-06 | #REF! | #REF!
8 | BSCT-Article-07 | #REF! | #REF!
9 | BSCT-Article-08 | #REF! | #REF!
10 | BSCT-Article-09 | #REF! | #REF!
11 | BSCT-Article-10 | #REF! | #REF!
12 | BSCT-Article-11 | #REF! | #REF!
13 | BSCT-Article-12 | #REF! | #REF!
14 | BSCT-Article-13 | #REF! | #REF!
15 | BSCT-Article-14 | #REF! | #REF!
16 | RCPTF-Article-01 | #REF! | #REF!
17 | RCPTF-Article-02 | #REF! | #REF!
18 | RCPTF-Article-03 | #REF! | #REF!
19 | RCPTF-Article-04 | #REF! | #REF!
20 | RCPTF-Article-05 | #REF! | #REF!
21 | RCPTF-Article-06 | #REF! | #REF!
22 | DCLNF-Article-01 | #REF! | #REF!
23 | DCLNF-Article-02 | #REF! | #REF!
24 | DCLNF-Article-03 | #REF! | #REF!
25 | DCLNF-Article-04 | #REF! | #REF!
26 | CBSP-Article-01 | #REF! | #REF!
27 | CBSP-Article-02 | #REF! | #REF!
28 | CBSP-Article-03 | #REF! | #REF!
29 | CBSP-Article-04 | #REF! | #REF!
30 | CBSP-Article-05 | #REF! | #REF!
31 | CBSP-Article-06 | #REF! | #REF!
32 | EXBSP-Article-01 | #REF! | #REF!
33 | EXBSP-Article-02 | #REF! | #REF!
34 | EXBSP-Article-03 | #REF! | #REF!
35 | EXBSP-Article-04 | #REF! | #REF!
36 | EXBSP-Article-05 | #REF! | #REF!
37 | EXBSP-Article-06 | #REF! | #REF!
38 | EXBSP-Article-07 | #REF! | #REF!
39 | EXBSP-Article-08 | #REF! | #REF!
40 | EXBSP-Article-09 | #REF! | #REF!
41 | EXBSP-Article-10 | #REF! | #REF!
42 | EXBSP-Article-11 | #REF! | #REF!
43 | EXBSP-Article-12 | #REF! | #REF!
44 | EXBSP-Article-13 | #REF! | #REF!
45 | EXBSP-Article-14 | #REF! | #REF!
46 | EXBSP-Article-15 | #REF! | #REF!
47 | EXBSP-Article-16 | #REF! | #REF!
48 | EXBSP-Article-17 | #REF! | #REF!
49 | EXBSP-Article-18 | #REF! | #REF!
50 | BCR-Article-01 | #REF! | #REF!
51 | BCR-Article-02 | #REF! | #REF!
52 | BCR-Article-03 | #REF! | #REF!
53 | UKN-Article-01 | #REF! | #REF!
54 | UKN-Article-02 | #REF! | #REF!
55 | UKN-Article-03 | #REF! | #REF!
56 | UKN-Article-04 | #REF! | #REF!
57 | UKN-Article-05 | #REF! | #REF!
58 | UKN-Article-06 | #REF! | #REF!
59 | UKN-Article-07 | #REF! | #REF!
60 | NLR-Article-01 | #REF! | #REF!
61 | NLR-Article-02 | #REF! | #REF!
62 | NLR-Article-03 | #REF! | #REF!
63 | NLR-Article-04 | #REF! | #REF!
64 | NLR-Article-05 | #REF! | #REF!
65 | NLR-Article-06 | #REF! | #REF!
66 | NLR-Article-07 | #REF! | #REF!
67 | BT-Demand-01 | #REF! | #REF!
68 | BT-Demand-02 | #REF! | #REF!
69 | BT-Demand-03 | #REF! | #REF!
70 | BT-Demand-06 | #REF! | #REF!
71 | CBSP-Demand-01 | #REF! | #REF!
72 | CBSP-Demand-02 | #REF! | #REF!
73 | CBSP-Demand-03 | #REF! | #REF!
74 | CBSP-Demand-04 | #REF! | #REF!
75 | CBSP-Demand-05 | #REF! | #REF!
76 | CBSP-Demand-06 | #REF! | #REF!
77 | CBSP-Demand-07 | #REF! | #REF!
78 | CBSP-Demand-08 | #REF! | #REF!
79 | CBSP-Demand-09 | #REF! | #REF!
80 | CBSP-Demand-10 | #REF! | #REF!
81 | CBSP-Demand-11 | #REF! | #REF!
82 | CBSP-Demand-12 | #REF! | #REF!
83 | CBSP-Demand-13 | #REF! | #REF!
84 | CBSP-Demand-14 | #REF! | #REF!
85 | CBSP-Demand-15 | #REF! | #REF!
86 | CBSP-Demand-16 | #REF! | #REF!
87 | CBSP-Demand-17 | #REF! | #REF!
88 | CBSP-Demand-18 | #REF! | #REF!
89 | CBSP-Demand-19 | #REF! | #REF!
90 | EXBSP-Demand-01 | #REF! | #REF!
91 | EXBSP-Demand-02 | #REF! | #REF!
92 | EXBSP-Demand-03 | #REF! | #REF!
93 | EXBSP-Demand-04 | #REF! | #REF!
94 | EXBSP-Demand-05 | #REF! | #REF!
95 | EXBSP-Demand-06 | #REF! | #REF!
96 | EXBSP-Demand-07 | #REF! | #REF!
97 | EXBSP-Demand-08 | #REF! | #REF!
98 | EXBSP-Demand-09 | #REF! | #REF!
99 | EXBSP-Demand-10 | #REF! | #REF!
100 | EXBSP-Demand-11 | #REF! | #REF!
101 | EXBSP-Demand-12 | #REF! | #REF!
102 | EXBSP-Demand-13 | #REF! | #REF!
103 | EXBSP-Demand-14 | #REF! | #REF!
104 | EXBSP-Demand-15 | #REF! | #REF!
105 | EXBSP-Demand-16 | #REF! | #REF!
106 | EXBSP-Demand-17 | #REF! | #REF!
107 | EXBSP-Demand-18 | #REF! | #REF!
108 | RUKN-Demand-01 | #REF! | #REF!
109 | RUKN-Demand-02 | #REF! | #REF!
110 | RUKN-Demand-03 | #REF! | #REF!
111 | RUKN-Demand-04 | #REF! | #REF!
112 | RUKN-Demand-05 | #REF! | #REF!
113 | RUKN-Demand-06 | #REF! | #REF!
114 | RUKN-Demand-07 | #REF! | #REF!
115 | INSUF-Demand-01 | #REF! | #REF!
116 | INSUF-Demand-02 | #REF! | #REF!
117 | INSUF-Demand-03 | #REF! | #REF!
118 | FLIP-Article-01 | #REF! | #REF!
119 | FLIP-Article-02 | #REF! | #REF!
120 | FLIP-Demand-01 | #REF! | #REF!
121 | FLIP-Demand-02 | #REF! | #REF!
122 | OTHER-01 | #REF! | #REF!
123 | OTHER-02 | #REF! | #REF!
124 | OTHER-03 | #REF! | #REF!
125 | OTHER-04 | #REF! | #REF!
126 | OTHER-05 | #REF! | #REF!

## Sheet3 (hidden)
Test Name: | Receptacle Full - Article Based
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Assume the receptacle being full | Tompkins | [9 empty] | This is simulating a chute being full, actual testing of the photoeye will occur in UAT
2 | Initiate Closeout of the Receptacle | Tompkins | Click on the Close Menu Option, click on the location name and then click on the Close button |  |  |  | List of Locations eligible to close will be displayed and after selecting the location and the close button, the screen transitions to the next screen |  |  |  |  | Assume you are already logged into the handheld device and you are already scanned into the appropriate Takeaway zone.
3 | Continue with Closeout of the Receptacle by following menu prompts | Tompkins | Scan the Receptacle KC1 Barcode and click Submit |  |  |  | The barcode data will populate in the Scan Container to Close field
4 | Finalize the Closeout of the Receptacle | Tompkins | Visually inspect the green Container Closed successfully banner appeared |  |  |  | The Receptacle will be closed, indicated by the Container closed successfully green banner and the screen will transition to allow you to scan a new receptacle into the location
5 | Validate that a Container Status message (87 message is sent to 1WMS) | Tompkins | Validate the Container Status message is in IoT log |  |  |  | Validate that a Container Status message is sent to 1WMS such as the below example. Validate the Container KC1 barcode, orderID and StagedLocation {"companyId":"Kmart","facilityId":"9751P","messageNumber":1234567891,"messageCode":"3004","message Desc":"CONTAINER_STATUS","orderId":6666,"containerId":"9541234567000000555","containerStatus":"E XIT_STAGING_LOCATION","stagedLocation":"1A107","userId":"","module":"WI","closeoutReason":"", "message_ts":"2018-01-29T23:07:02.997"}
5 | Receive and Validate 87 Message | Kmart | Check 87 message (Ross how?) [RG 22/4/20 Option 759 Mailroom will show incoming 87. |  |  |  | 87 Message matches API format |  |  |  |  | Refer 87 reference guide
Sortation Attributes
SIT Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | Hanger? | Wt | Cube | Has Event? | Liq | Fragile | DG | Allowable Cluster | Package | PO#
RCPTF-Article-05 | Test that when the receptacle is full but not removed and is NOT available for sorting | Tompkins Only | BSCT-Article-04 |  |  | Not executed
RCPTF-Article-02 | Test that on closing a receptacle tWes sends -87- message to 1WMS | Tompkins Only | BSCT-Article-04 |  |  | Not executed