## Test Summary
CN80 Scanner Testing
Test Name | Test Purpose | Comment | DC Team | Head Office Team | Vendor Team | Worksheet Reference | Not executed | In progress | Pass | Fail | Pending | Retest | Total
Pre-Work | Preparation for below tests prior to test day |  | DC Operations | Support |  | Pre-Work
Standard CN80 Scan Tests | Regression test of 1D labels and standard 2D label tests | 1-2 devices pre full rollout | DC Operations |  |  | Standard Scan | 5 | [5 empty] | 5
Standard CN80 Consolidation Tests | Consolidation tests including minor speed test | 1-2 devices pre full rollout | DC Operations |  |  | Consolidation | 2 | [5 empty] | 2
Standard CN80 Voice Tests | Tests of voice scanning, including minor speed test | 1-2 devices pre full rollout | DC Operations |  |  | Voice | 1 | [5 empty] | 1
All CN80 Verification Tests | Minimum verification of all CN80s with 1D and 2D | All devices | DC Operations |  |  | CN80 All | 3 | [5 empty] | 3
tWes CN80 Closeout Tests | Use of tWes Closeout scanning in Wiri DC | Test only at Wiri DC | DC Operations | Support | Support | NZ Wiri Closeout | 1 | [5 empty] | 1
[6 empty] | Total | 12 | 0 | 0 | 0 | 0 | 0 | 12
[6 empty] | Percentage | 100% | 0% | 0% | 0% | 0% | 0%

## Pre-Work
Test Sheet | Product Required | Quantity | Comment | Label Source
Standard Scan | 91 Labelled carton | 1 | Current label | DC
Standard Scan | 00 Labelled carton | 1 | Current label | DC
Standard Scan | 1D 92/93 Labelled carton | 1 | Current label | DC Overseas Stock
Standard Scan | 2D 92/93 Labelled carton | 1 | Current label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Standard Scan | 2D 92/93 Labelled polybag | 1 | Current label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Consolidation | 2D 92/93 Labelled carton | 1 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Consolidation | 2D 92/93 Labelled apparel polybags | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
Consolidation | 2D 92/93 Labelled apparel polybags | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
CN80 All | 91 Labelled carton | 1 | Current label, each device can scan the same label | DC
CN80 All | 1D 92/93 Labelled carton | 1 | Current label, each device can scan the same label | DC Overseas Stock
CN80 All | 2D 92/93 Labelled carton | 1 | Current label, each device can scan the same label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock
New Zealand Wiri DC Only
NZ Wiri Closeout | 2D 92/93 Labelled carton | Multiple | KC1s ready for close out. Each device can closeout one KC1. | Closeout process.

## Standard Scan
Test Name: | Standard CN80 Scan Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Scan_01 | Use scanner to scan a 91 SSCC barcode | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 91 SSCC is displayed.
CN80Scan_02 | Use scanner to scan a 00 SSCC barcode | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 00 SSCC is displayed.
CN80Scan_03 | Use scanner to scan the 93 portion of a 1D 92/93 SSCC barcode | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
CN80Scan_04 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
CN80Scan_05 | Use scanner to scan a 2D 92/93 SSCC barcode on a polybag | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F5=SSCC Enquiry | DC Operator | SSCC Enquiry entry screen displays |  |  |  | SSCC Enquiry Entry screen displays
3 | Scan the SSCC barcode being tested | DC Operator | Ensure that the cursor is at the beginning of the SSCC Enquiry field, and use the CN80 scanner to scan the barcode. |  |  |  | Appropriate 20 long SSCC displays, and shows details of the SCM within 1WMS.

## Consolidation
Test Name: | Standard CN80 Consolidaton Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Cons_01 | Use scanner to consolidate a 2D 93 carton in Non-Cons | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 93 SSCC is displayed when scanned. 93 SSCC is consolidated to the consolidation.
CN80Cons_02 | Use scanner to consolidate a 2D 93 apparel polybags in apparel area. | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 10 | As Below | 93 SSCC is displayed when scanned. 93 SSCC is consolidated to the consolidation.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F3=Consolidation, then F1=Consolidate, then choose the appropriate consolidation option | DC Operator | Consolidation function opens |  |  |  | Consolidation function opens
3 | Enter LA Mode using F7 | DC Operator | LA Mode displays |  |  |  | LA Mode is shown in message area of the RF device
4 | Scan the SSCC | DC Operator | Details of the next store requiring the SSCC are displayed. |  |  |  | SSCC Next Store details displayed |  |  |  |  | NB: This step can be skipped if done for an earlier test
5 | Scan the Consolidation for the Next Store | DC Operator | Consolidation SSCC is entered |  |  |  | Consolidation is displayed |  |  |  |  | NB: This step can be skipped if done for an earlier test
6 | Scan the SSCC being tested | DC Operator | Valiate that 93 SSCC is entered and consolidated. Validate that SSCC count down details are displayed or GO TO Next store details are displayed. |  |  |  | Last SSCC is shown as the just scanned 93 SSCC. X to Go is displayed and/or Go To next store details are displayed |  |  |  |  | If Go To next store , then go there for consolidating the next product.

## Voice
Test Name: | Standard CN80 Voice Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Voice_01 | Use scanner in voice mode to consolidate a 2D 93 polybag in Apparel area | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 10 | As Below | See below.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Sign on to voice consolidation | DC Operator | Responds with Scan SSCC or Consolidation |  |  |  | SSCC or Consolidation prompt returned
3 | Say "LA Mode" | DC Operator | Responds with "LA Mode, Scan SSCC" |  |  |  | LA Mode, Scan SSCC returned
4 | Scan the test SSCC | DC Operator | Responds with the cluster, next store and the quantity |  |  |  | Cluster nn, Next store nnnn, quantity n |  |  |  |  | NB: This step can be skipped if done for an earlier test
5 | Scan the Consolidation for the Next Store | DC Operator | Responds with the Store number and confirms LA Mode |  |  |  | Store nnnn, LA Mode |  |  |  |  | NB: This step can be skipped if done for an earlier test
6 | Scan the SSCC being tested | DC Operator | Responds with a count down (x to go) May request that you go to another store. |  |  |  | n to go. N to go, go to store nnnn |  |  |  |  | If Go To next store , then go there for consolidating the next product.
7 | After full test confirm SSCCs are consolidated using RF SSCC Enquiry | DC Operator | Validate that the SSCCs show as being resolved to the appropriate store and consolidated |  |  |  | SSCCs do not show as "Not Linked to Store" SSCC status is CO

## CN80 All
Test Name: | All CN80 Verification Tests | [All CN80 devices] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80All_01 | Use scanner to scan a 91 SSCC barcode | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 91 SSCC is displayed.
CN80All_02 | Use scanner to scan the 93 portion of a 1D 92/93 SSCC barcode | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
CN80All_03 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F5=SSCC Enquiry | DC Operator | SSCC Enquiry entry screen displays |  |  |  | SSCC Enquiry Entry screen displays |  |  |  |  | If at Reject lane of a sorter, use F2, then F8=Reject Enquiry instead of SSCC enquiry
3 | Scan the SSCC barcode being tested | DC Operator | Ensure that the cursor is at the beginning of the SSCC Enquiry field, and use the CN80 scanner to scan the barcode. |  |  |  | Appropriate 20 long SSCC displays, and shows details of the SCM within 1WMS.

## NZ Wiri Closeout
Test Name: | CN80 tWes Closeout tests | [All CN80 devices] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Close_01 | Close a KC1 receptacle that is full | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. Close occurs. Consolidation Label prints.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Switch to the tWes application on the CN80 | DC Operator | tWes application starts and presents sign in screen |  |  |  | tWes sign in screen is displayed
2 | Sign on to the close out scanner | DC Operator | Login to the close out scanner with your user name and password, IF NOT ALREADY LOGGED IN You will need to scan into a zone |  |  |  | Login is successful |  |  |  |  | User name is first name.lastname@dc9751 e.g. john.herbert@dc9571 NB: if sign on errors, tap the tWes logo 5+ times in quick succession and check that the endpoint is https://kmart-prod.sensorthink.com If it is different, change it and preset Set, then Close and try signing in again [this is in case some CN80s are not yet configured for tWes]
3 | Stop sorting to this location | DC Operator | Click the stop button at the sort outlet
4 | Close a KC1 | DC Operator | Using the close out scanner Scan the sort outlet Scan the KC1# barcode |  |  |  | Container is closed successfullly |  |  |  |  | Can close a partially full KC1 and print its label, then reassign to the same location if needed (dispose of the consolidation label if you do this as the count and weight will be wrong - it can be reprinted when next closed)
5 | Physically remove the KC1 from the sort outlet | DC Operator | Physically remove the KC1 from its position with an electronic pallet jack |  |  |  | KC1 is not in the sort outlet
6 | Switch to 1WMS, sign in, use F3=Consolidate, and F7=Prt KC Cons Label. Scan the KC1 barcode and print the label | DC Operator | Validate that the label prints and apply the label |  |  |  | Consolidation label for the KC1 prints.

## Cntl Card (hidden)
Test Status
Not executed
In progress
Pass
Fail
Pending
Retest
NA

## Test Plan (hidden)
Test Plan
Nbr of days for SIT | 25
Total Nbr of SIT Test Cases | #REF!
Nbr of Test Cases / Day | #REF!
Nbr | Test Case ID | Day | Work Field for Conditional Formatting
1 | BSCT-Article-01 | #REF! | #REF!
2 | BSCT-Article-02A | #REF! | #REF!
3 | BSCT-Article-02B | #REF! | #REF!
4 | BSCT-Article-03 | #REF! | #REF!
5 | BSCT-Article-04 | #REF! | #REF!
6 | BSCT-Article-05 | #REF! | #REF!
7 | BSCT-Article-06 | #REF! | #REF!
8 | BSCT-Article-07 | #REF! | #REF!
9 | BSCT-Article-08 | #REF! | #REF!
10 | BSCT-Article-09 | #REF! | #REF!
11 | BSCT-Article-10 | #REF! | #REF!
12 | BSCT-Article-11 | #REF! | #REF!
13 | BSCT-Article-12 | #REF! | #REF!
14 | BSCT-Article-13 | #REF! | #REF!
15 | BSCT-Article-14 | #REF! | #REF!
16 | RCPTF-Article-01 | #REF! | #REF!
17 | RCPTF-Article-02 | #REF! | #REF!
18 | RCPTF-Article-03 | #REF! | #REF!
19 | RCPTF-Article-04 | #REF! | #REF!
20 | RCPTF-Article-05 | #REF! | #REF!
21 | RCPTF-Article-06 | #REF! | #REF!
22 | DCLNF-Article-01 | #REF! | #REF!
23 | DCLNF-Article-02 | #REF! | #REF!
24 | DCLNF-Article-03 | #REF! | #REF!
25 | DCLNF-Article-04 | #REF! | #REF!
26 | CBSP-Article-01 | #REF! | #REF!
27 | CBSP-Article-02 | #REF! | #REF!
28 | CBSP-Article-03 | #REF! | #REF!
29 | CBSP-Article-04 | #REF! | #REF!
30 | CBSP-Article-05 | #REF! | #REF!
31 | CBSP-Article-06 | #REF! | #REF!
32 | EXBSP-Article-01 | #REF! | #REF!
33 | EXBSP-Article-02 | #REF! | #REF!
34 | EXBSP-Article-03 | #REF! | #REF!
35 | EXBSP-Article-04 | #REF! | #REF!
36 | EXBSP-Article-05 | #REF! | #REF!
37 | EXBSP-Article-06 | #REF! | #REF!
38 | EXBSP-Article-07 | #REF! | #REF!
39 | EXBSP-Article-08 | #REF! | #REF!
40 | EXBSP-Article-09 | #REF! | #REF!
41 | EXBSP-Article-10 | #REF! | #REF!
42 | EXBSP-Article-11 | #REF! | #REF!
43 | EXBSP-Article-12 | #REF! | #REF!
44 | EXBSP-Article-13 | #REF! | #REF!
45 | EXBSP-Article-14 | #REF! | #REF!
46 | EXBSP-Article-15 | #REF! | #REF!
47 | EXBSP-Article-16 | #REF! | #REF!
48 | EXBSP-Article-17 | #REF! | #REF!
49 | EXBSP-Article-18 | #REF! | #REF!
50 | BCR-Article-01 | #REF! | #REF!
51 | BCR-Article-02 | #REF! | #REF!
52 | BCR-Article-03 | #REF! | #REF!
53 | UKN-Article-01 | #REF! | #REF!
54 | UKN-Article-02 | #REF! | #REF!
55 | UKN-Article-03 | #REF! | #REF!
56 | UKN-Article-04 | #REF! | #REF!
57 | UKN-Article-05 | #REF! | #REF!
58 | UKN-Article-06 | #REF! | #REF!
59 | UKN-Article-07 | #REF! | #REF!
60 | NLR-Article-01 | #REF! | #REF!
61 | NLR-Article-02 | #REF! | #REF!
62 | NLR-Article-03 | #REF! | #REF!
63 | NLR-Article-04 | #REF! | #REF!
64 | NLR-Article-05 | #REF! | #REF!
65 | NLR-Article-06 | #REF! | #REF!
66 | NLR-Article-07 | #REF! | #REF!
67 | BT-Demand-01 | #REF! | #REF!
68 | BT-Demand-02 | #REF! | #REF!
69 | BT-Demand-03 | #REF! | #REF!
70 | BT-Demand-06 | #REF! | #REF!
71 | CBSP-Demand-01 | #REF! | #REF!
72 | CBSP-Demand-02 | #REF! | #REF!
73 | CBSP-Demand-03 | #REF! | #REF!
74 | CBSP-Demand-04 | #REF! | #REF!
75 | CBSP-Demand-05 | #REF! | #REF!
76 | CBSP-Demand-06 | #REF! | #REF!
77 | CBSP-Demand-07 | #REF! | #REF!
78 | CBSP-Demand-08 | #REF! | #REF!
79 | CBSP-Demand-09 | #REF! | #REF!
80 | CBSP-Demand-10 | #REF! | #REF!
81 | CBSP-Demand-11 | #REF! | #REF!
82 | CBSP-Demand-12 | #REF! | #REF!
83 | CBSP-Demand-13 | #REF! | #REF!
84 | CBSP-Demand-14 | #REF! | #REF!
85 | CBSP-Demand-15 | #REF! | #REF!
86 | CBSP-Demand-16 | #REF! | #REF!
87 | CBSP-Demand-17 | #REF! | #REF!
88 | CBSP-Demand-18 | #REF! | #REF!
89 | CBSP-Demand-19 | #REF! | #REF!
90 | EXBSP-Demand-01 | #REF! | #REF!
91 | EXBSP-Demand-02 | #REF! | #REF!
92 | EXBSP-Demand-03 | #REF! | #REF!
93 | EXBSP-Demand-04 | #REF! | #REF!
94 | EXBSP-Demand-05 | #REF! | #REF!
95 | EXBSP-Demand-06 | #REF! | #REF!
96 | EXBSP-Demand-07 | #REF! | #REF!
97 | EXBSP-Demand-08 | #REF! | #REF!
98 | EXBSP-Demand-09 | #REF! | #REF!
99 | EXBSP-Demand-10 | #REF! | #REF!
100 | EXBSP-Demand-11 | #REF! | #REF!
101 | EXBSP-Demand-12 | #REF! | #REF!
102 | EXBSP-Demand-13 | #REF! | #REF!
103 | EXBSP-Demand-14 | #REF! | #REF!
104 | EXBSP-Demand-15 | #REF! | #REF!
105 | EXBSP-Demand-16 | #REF! | #REF!
106 | EXBSP-Demand-17 | #REF! | #REF!
107 | EXBSP-Demand-18 | #REF! | #REF!
108 | RUKN-Demand-01 | #REF! | #REF!
109 | RUKN-Demand-02 | #REF! | #REF!
110 | RUKN-Demand-03 | #REF! | #REF!
111 | RUKN-Demand-04 | #REF! | #REF!
112 | RUKN-Demand-05 | #REF! | #REF!
113 | RUKN-Demand-06 | #REF! | #REF!
114 | RUKN-Demand-07 | #REF! | #REF!
115 | INSUF-Demand-01 | #REF! | #REF!
116 | INSUF-Demand-02 | #REF! | #REF!
117 | INSUF-Demand-03 | #REF! | #REF!
118 | FLIP-Article-01 | #REF! | #REF!
119 | FLIP-Article-02 | #REF! | #REF!
120 | FLIP-Demand-01 | #REF! | #REF!
121 | FLIP-Demand-02 | #REF! | #REF!
122 | OTHER-01 | #REF! | #REF!
123 | OTHER-02 | #REF! | #REF!
124 | OTHER-03 | #REF! | #REF!
125 | OTHER-04 | #REF! | #REF!
126 | OTHER-05 | #REF! | #REF!

## Sheet3 (hidden)
Test Name: | Receptacle Full - Article Based
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Assume the receptacle being full | Tompkins | [9 empty] | This is simulating a chute being full, actual testing of the photoeye will occur in UAT
2 | Initiate Closeout of the Receptacle | Tompkins | Click on the Close Menu Option, click on the location name and then click on the Close button |  |  |  | List of Locations eligible to close will be displayed and after selecting the location and the close button, the screen transitions to the next screen |  |  |  |  | Assume you are already logged into the handheld device and you are already scanned into the appropriate Takeaway zone.
3 | Continue with Closeout of the Receptacle by following menu prompts | Tompkins | Scan the Receptacle KC1 Barcode and click Submit |  |  |  | The barcode data will populate in the Scan Container to Close field
4 | Finalize the Closeout of the Receptacle | Tompkins | Visually inspect the green Container Closed successfully banner appeared |  |  |  | The Receptacle will be closed, indicated by the Container closed successfully green banner and the screen will transition to allow you to scan a new receptacle into the location
5 | Validate that a Container Status message (87 message is sent to 1WMS) | Tompkins | Validate the Container Status message is in IoT log |  |  |  | Validate that a Container Status message is sent to 1WMS such as the below example. Validate the Container KC1 barcode, orderID and StagedLocation {"companyId":"Kmart","facilityId":"9751P","messageNumber":1234567891,"messageCode":"3004","message Desc":"CONTAINER_STATUS","orderId":6666,"containerId":"9541234567000000555","containerStatus":"E XIT_STAGING_LOCATION","stagedLocation":"1A107","userId":"","module":"WI","closeoutReason":"", "message_ts":"2018-01-29T23:07:02.997"}
5 | Receive and Validate 87 Message | Kmart | Check 87 message (Ross how?) [RG 22/4/20 Option 759 Mailroom will show incoming 87. |  |  |  | 87 Message matches API format |  |  |  |  | Refer 87 reference guide
Sortation Attributes
SIT Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | Hanger? | Wt | Cube | Has Event? | Liq | Fragile | DG | Allowable Cluster | Package | PO#
RCPTF-Article-05 | Test that when the receptacle is full but not removed and is NOT available for sorting | Tompkins Only | BSCT-Article-04 |  |  | Not executed
RCPTF-Article-02 | Test that on closing a receptacle tWes sends -87- message to 1WMS | Tompkins Only | BSCT-Article-04 |  |  | Not executed