## Test Summary
2D Label Testing
Test Name | Test Purpose | Comment | DC Team | Head Office Team | Vendor Team | Worksheet Reference | Not executed | In progress | Pass | Fail | Pending | Retest | Total
Pre-Work | Preparation for below tests prior to test day |  | DC Operations | Support |  | Pre_Work
Printer test of 2D barcodes | Testing printing of 1WMS generated 2D barcodes |  | DC Operations |  |  | Printers | 0 | 0 | 2 | 0 | 0 | 0 | 2
Sorter Standard | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | Sorter_Standard | 0 | 0 | 6 | 0 | 0 | 0 | 6
Sorter Volume Rates | Volume testing of quality 2D labels |  | DC Ops, Sorter Manager | Support | Support | Sorter_Volume | 0 | 0 | 2 | 0 | 0 | 0 | 2
Sorter Duplicate label tests | Heirarchy testing of duplicates of 1D and 2D labels | Test at one site only | DC Ops, Sorter Manager | Support | Support | Sorter_Dups | 0 | 0 | 6 | 0 | 0 | 0 | 6
Sorter Bad Label Comparison tests | Comparison of performance of 2D and 1D 92/93 labels | Test at one site only | DC Ops, Sorter Manager | Support | Support | Sorter_Label_Compare | 0 | 0 | 24 | 1 | 0 | 0 | 25
CN80 Standard | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | CN80_Standard | 0 | 0 | 6 | 0 | 0 | 0 | 6
Consolidaton Tests | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | Consolidation | 0 | 0 | 5 | 0 | 0 | 0 | 5
CN80 Voice Tests | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | CN80_Voice | 0 | 0 | 0 | 0 | 0 | 0 | 0
Std Ring Scan | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | Std_Ring_Scan | 0 | 0 | 5 | 0 | 0 | 0 | 5
Vocollect All | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | Vocollect_All | 0 | 0 | 3 | 0 | 0 | 0 | 3
Std VM1A | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | Std_VM1A | 0 | 0 | 1 | 0 | 0 | 0 | 1
[6 empty] | Total | 0 | 0 | 60 | 1 | 0 | 0 | 61
[6 empty] | Percentage | 0% | 0% | 98.36% | 1.639% | 0% | 0% | 100%

## Pre_Work
Test Sheet | Product Required | Quantity | Qty from Cont | Comment | Label Source | Label Type | PO | Keycode | Qty | Remaining
Printers | 92/93 UNRES Pick and Pack in 351 | 3 |  |  | DC | Generated
Sorter_Standard | 91 Labelled sortable medium sized carton | 5 |  | Ensure that label messages are inducted to sort director | DC | 1D 91
Sorter_Standard | 00 Labelled sortable medium sized carton | 5 |  | Ensure that label messages are inducted to sort director | DC | 1D 00
Sorter_Standard | 1D 92/93 Labelled sortable medium sized carton | 5 | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock | 1D 92/93 | PO 29308717 | 43228928
Sorter_Standard | 2D 92/93 Labelled sortable medium sized carton | 5 | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 | PO 29308717 | 43228928 | 5 | 81
Sorter_Standard | 2D 92/93 Labelled sortable small sized carton | 5 | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Sorter_Standard | 2D 92/93 Labelled sortable large sized carton | 5 | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 | PO 19165030 | 43161836 | 5 | 108
Sorter_Standard | 2D 92/93 Labelled sortable polybag (cardboard backed) | 5 | 5 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 | PO 19165030 | 43228935 | 5 | 31 | Ensure not in Pick and apply to any polybag
Sorter_Standard | 2D 91 Labelled sortatable Flow product. | 5 |  | Ensure that label messages are inducted to sort director | 2D label printed at DC | 2D 91 Flow
Sorter_Volume | 2D 92/93 Labelled sortable cartons | 1000 | 1000 | Ensure that label messages are inducted to sort director | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 | PO 19208717 | 43161836 | 145 | 0
Sorter_Volume | 2D 92/93 Labelled sortable cartons | 1000 | 1000 | Mix with below, ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 | PO 19199023 | 43228928 | 151 | 0
Sorter_Volume | 1D 92/93 Labelled sortable cartons | 1000 | 1000 | Mix with above, ensure messages are inducted | DC Overseas Stock | 1D 92/93
Sorter_Dups | 2 x2D 92/93 Labelled sorter cartons | 1 | 1 | 2 of same label applied. Inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 | PO 19165030 | 43161836 | 2 | 106
Sorter_Dups | 92/93 Labelled carton + 2D label | 1 | 1 | Leave 1D label and apply same as 2D on another side. Inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 1D + 2D 92/93 | PO 19165030 | 43161836 | 1 | 105
Sorter_Dups | Replace 92/93 label with 2D + add 91 label | 1 | 1 | PnP genuine 92/93 requiring 91 labels. Both inducted i.e another pick with 92/93 label required | Replace 92/93 with 2D; Add 91 Label - DC. CBX Generated for 2D for that stock | 2D 92/93 + 1D 91 | PO 19165030 | 43161836 | 1 | 104
Sorter_Dups | Local 00 labelled stock + 2D label | 1 | 1 | Both inducted. 2D label can be random i.e. not for this stock. | Standard 00 labelled stock, PDF Generated 2D label for other stock from CBX | 2D 92/93 + 1D 00 | PO 19165030 | 43161836 | 1 | 103
Sorter_Dups | Overseas stock with other 00 barcode + 2D label | 1 | 1 | 00 barcode not SSCC. Inducted 92/93. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 + Other | PO 19165030 | 43161836 | 1 | 102
Sorter_Dups | 1D 92/93 Labelled carton + 2D label | 1 | 1 | 2D label not for this stock, applied on another side. Both inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 + 1D 92/93 | PO 19165030 | 43161836 | 1 | 101
Sorter_Dups | 2 x 2D 92/93 Labelled carton. | 1 | 1 | 1 x 2D for stock, 1 x 2D for other stock. Both inducted. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for stock and other stock. | 2D 92/93 | PO 19165030 | 43161836 | 30 | 71
#REF! | 2D 92/93 labelled cartons | 33 | 33 | Prepare per test cases, and induct, requires packing tape too. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Sorter_Label_Compare | 2D 92/93 labelled cartons - same position as below | 30 | 30 | Prepare per test cases, and induct, requires packing tape too. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Sorter_Label_Compare | 1D 92/93 labelled cartons - same position as above | 30 | 30 | Prepare per test cases, and induct, requires packing tape too. These are twins of the 2D labelled stock, and must be prepared in exactly the same way as the 2D labelled stock for comparison | DC Overseas Stock for same products as 2D labelled stock. | 1D 92/93
CN80_Standard | 91 Labelled carton | 1 | 1 | Current label | DC | 1D 91
CN80_Standard | 00 Labelled carton | 1 | 1 | Current label | DC | 1D 00
CN80_Standard | 1D 92/93 Labelled carton | 1 | 1 | Current label | DC Overseas Stock | 1D 92/93
CN80_Standard | 2D 92/93 Labelled carton | 1 | 1 | Current label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
CN80_Standard | 2D 92/93 Labelled polybag | 1 | 1 | Current label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
CN80_Standard | 2D 91 Flow Labelled carton | 1 | 1 | Current label | DC | 2D 91 Flow
CN80_Standard | 91 labelled Pallet LPN label | 1 |  | Currently on product Pallet | DC | 1D 91 LPN
Consolidation | 2D 92/93 Labelled carton | 1 | 1 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Consolidation | 2D 92/93 Labelled apparel polybags | 10 | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Consolidation | 2D 92/93 Labelled apparel polybags | 10 | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
CN80_Voice | 2D 92/93 Labelled polybag | 1 | 1 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
CN80_Voice | 91 Labelled polybag + 2D Flow 91 | 2 |  | Currently Labelled stock | DC | 1D 91 + 2D 91
CN80_Voice | 1D 92/93 Labelled Polybag | 1 | 1 | Current label | DC Overseas Stock | 1D 92/93
Std_Ring_Scan | 91 Labelled carton + 2D Flow 91 | 2 |  | Currently Labelled stock | DC | 1D 91 + 2D 91
Std_Ring_Scan | 00 Labelled carton | 1 |  | Currently Labelled stock | DC | 1D 00
Std_Ring_Scan | 1D 92/93 Labelled carton | 1 | 1 | Currently Labelled stock | DC Overseas Stock | 1D 92/93
Std_Ring_Scan | 2D 92/93 Labelled carton | 1 | 1 | Currently Labelled stock, replace with 2D label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Std_Ring_Scan | 2D 92/93 Labelled polybag | 1 | 1 | Currently Labelled stock, replace with 2D label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Consolidation | 2D 92/93 Labelled carton | 1 | 1 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Consolidation | 2D 92/93 Labelled apparel polybags | 10 | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Consolidation | 2D 92/93 Labelled apparel polybags | 5 | 5 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Consolidation | 1D 92/93 Labelled apparel polybags | 5 | 5 | Ensure that product is manual mode, test during week, mix with above. | DC Overseas Stock | 1D 92/93
Vocollect_All | 91 Labelled carton + 2D Flow 91 | 2 |  | Currently Labelled stock, each device can scan same stock | DC | 1D 91 + 2D 91
Vocollect_All | 1D 92/93 Labelled carton | 1 | 1 | Currently Labelled stock, each device can scan same stock | DC Overseas Stock | 1D 92/93
Vocollect_All | 2D 92/93 Labelled carton | 1 | 1 | Currently Labelled stock, replace with 2D label, each device can scan same stock | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Std_VM1A | 91 Labelled carton | 1 |  | Current Label | DC | 1D 91
Std_VM1A | 00 Labelled carton | 1 |  | Current Label | DC | 1D 00
Std_VM1A | 1D 92/93 Labelled carton | 1 | 1 | Current Label | DC Overseas Stock | 1D 92/93
Std_VM1A | 2D 92/93 Labelled carton | 1 | 1 | Current Label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
Std_VM1A | 91 labelled Pallet LPN label | 1 |  | Currently on product Pallet | DC | 1D 91 LPN
Std_VM1A | 2D Flow 91 Labelled carton | 1 |  | Current Label | DC | 2D 91 Flow
Total Labels |  | 3212 | 3182

## Printers
Test Name: | Printer Test of 2D barcodes | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Print_1 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Printronix printer. | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | 2D Label prints
Print_2 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Intermec PC43D printer. | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | 2D Label prints
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Go to option 351 | DC Operator | Enters Pick Management |  |  |  | Enters Pick Management
2 | Enter option 7 and find UNRES stock with CC status | DC Operator | Enters Pick Management - SCMs |  |  |  | Enters Pick Management - SCMs
3 | Use option 9=Re-Print | DC Operator | Verify that label is printed from the approprate printer. Validate that the label is a 2D label |  |  |  | 2D label printed

## Sorter_Standard
Test Name: | Sorter Standard | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Sort_01 | Sort a 91 SSCC labelled medium carton product Place 5 items with 91 SSCCs on the sorter. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_02 | Sort a 00 SSCC labelled medium carton product Place 5 items with 00 SSCCs on the sorter. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_03 | Sort a 1D 92/93 SSCC labelled medium carton product Place 5 items with 92/93 SSCCs on the sorter. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_04 | Sort a 2D 92/93 SSCC labelled medium carton product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_05 | Sort a 2D 92/93 SSCC labelled small carton product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_06 | Sort a 2D 92/93 SSCC labelled large sortable carton product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Orientate as follows: 1. Label is facing up 2. Label is facing left 3. Label is facing right 4. Label is facing forwards 5. Label is facing backwards 43161836 | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 5 | As Below | All 5 SSCCs sort to store lanes
Sort_07 | Sort a 2D 92/93 SSCC labelled sortable polybag product Place 5 items with 92/93 SSCCs on the sorter. Re-print their labels and replace with 2D 92/93 labels if not already done so. Ensure that product is flipped to sorter (reset after the test) Orientate as follows: 1. Label is facing up Use 43228935 - check not picked first. Should reject. | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 1 | As Below | SSCC sorts to store lane
Sort_08 | Sort a 2D 91 Flow Label Use a test label | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | SSCC sorts to store lane
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Record product and orientation of the label(s) in this spreadsheet | DC Operator | Use felt pen to number each box according to orientation and/or record the SSCC number. |  |  |  | Product recorded |  |  |  |  | This is so that failed cases can be identified. 1D = Linear barcodes 2D = Square barcodes
2 | Place product on to the induct lane(s) in orientation described in the test. | DC Operator | Product enters the loop in desired orientation |  |  |  | Product enters the loop correctly
3 | Product enters the scanner tunnel | Sorter Manager | Sort Director shows the SSCC, and appropriate 00, 91 and/or 92/93 SSCC is displayed as scanned. |  |  |  | Product scans successfully |  |  |  |  | Products in all orientations need to scan successfully for the test to pass.
4 | Product sorts to the appropriate lane for the store | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director |  |  |  | Product sorts to the correct store lane
5 | Verify sort in option 36 | DC Operator | Option 36 shows the SSCC |  |  |  | SSCC is shown as sorted ok or shows the reject reason |  |  |  |  | Validates that the SSCC information is returned to 1WMS.
6 | Use Reject Enquiry function to scan the SSCC | DC Operator | Reject Enquiry shows that product sorted to the store, or shows reason for reject (can verify in SSCC Enquiry too). |  |  |  | Reject Enquiry show OK for store lanes, or reject reason |  |  |  |  | Validates that Dematic Sorter Reporting server has received the correct SSCC information.

## Sorter_Volume
Test Name: | Sorter Volume Rates | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Vol_01 | Process 1000 2D labelled cartons | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1000 | As Below | 99.9% sort to store lanes
Vol_02 | Process 1000 mixed 1D and 2D labelled cartons 50% of the cartons should be relabelled with 2D labels | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2000 | As Below | 99.9% of 2D labelled cartons sort to store lanes
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare 1000 cartons with labels as required by the test | DC Operator/ HO Support | 1000 cartons prepared for the test with labels applied Product data is inducted to the sorter |  |  |  | 1000 cartons per test with 2D labels prepared |  |  |  |  | Ensure that all product it is sortable and has fresh messages on the sorter.
2 | Place product on to the induct lane(s) with all barcodes in sortable positions (i.e. not facing downwards) | DC Operator | Use all induct lanes Verify that all cartons have barcodes in scannable positions |  |  |  | Around 250 cartons per lane. All cartons in scannable orientations
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC, and appropriate 00, 91 and/or 92/93 SSCC is displayed as scanned. |  |  |  | Product scans successfully
4 | Product sorts to the appropriate lane for the store | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director |  |  |  | Product sorts to the correct store lane
5 | Verify sort in option 36 and extract data | HO Support | Option 36 shows the SSCC Extract sorter data and verify all sorted ok. |  |  |  | SSCC is shown as sorted ok |  |  |  |  | Check for any rejects, and check causes. Test fails if there are 2D barcode read failures when scanned (excluding shadowing, priority conflict or other rejects not due to a bad read of the barcode)
113
145
151
86
495
[6 empty] | 403 | Processed on Web Sentinel ok

## Sorter_Dups
Test Name: | Sorter Priority label tests | [These tests only need to be done at the first Australian site] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Dup_01 | Process a carton with two 92/93 2D SSCC labels that have the same product and SSCC details | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | Priority Conflict
Dup_02 | Process a carton with one 1D 92/93 SSCC label and one 92/93 2D SSCC label that have the same product and SSCC details | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | Priority Conflict
Dup_03 | Process a carton with a 91 label and a 2D 92/93 SSCC label | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane shown on 91 label |  | 91 SSCC not in Sort Director, so consistent with current issue, it processed the 93.
Dup_04 | Process a carton with a sortable 00 label known to the sorter and a 2D 92/93 label | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | Carton rejects with priority conflict (local product should not sort with overseas label) |  | Sorted to 6666 (which ended up as reject)
Dup_05 | Process a carton with a 00 description (non-SSCC) barcode and a 2D 92/93 label | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 1 | As Below | Carton sorts to a store lane based on the 92/93 label |  | (No product)
Dup_06 | Process a carton with a 1D 92/93 SSCC and a 2D 92/93 with different products encoded in the labels (different 92). | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | Carton rejects with a priority conflict.
Dup_07 | Process a carton with two 2D SSCC labels that have different products encoded (different 92 SSCCs). One 2D label should be for the product in the box. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 1 | As Below | Carton rejects with a priority conflict.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare cartons with labels as identified in the test | DC Operator/ HO Support | Labels are placed on the cartons |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate
2 | Place product for test on to the induction lane(s) for the sorter with all barcodes in scannable positions | DC Operator | Barcode labels can be scanned by the sorter |  |  |  | All labels are in scannable positions
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC, and appropriate 00, 91 and/or 92/93 SSCC is displayed as scanned. |  |  |  | Product scans successfully
4 | Product sorts to the appropriate lane for the store or rejects depending on the test. | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director or to the reject lane. Validate that rejects are expected. |  |  |  | Product sorts to the correct store lane or reject lane. Only expected rejects sort to the reject lane.
5 | Verify sort in option 36 and validate rejects | HO Support | Option 36 shows the SSCC Validate rejected products |  |  |  | SSCC is shown in option 36. Only expected rejects are rejected.
6 | Verify reject cause at reject lane | DC Operator | Use Reject Enquiry to scan rejected cartons to determine the cause of the reject |  |  |  | SSCC scans ok. Reject cause is per the test expection (where appropriate).
7 | Black out incorrect label for Priority conflicts and re-sort the carton | DC Operator | Validate that carton sorts ok and does not return to the reject lane. |  |  |  | Remaining label scans ok Product sorts to a store lane.

## Sorter_Label_Compare
Test Name: | Sorter Bad Label Comparison | [These tests only need to be done at the first Australian site] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Result | 2D Score | 1D Score | Total | Special Features of the product | Barcode/s
Comp_01 | Label Placement Edge compare 1 Process a carton with a 92/93 2D label placed with the full label at the edge of the carton. Process a second carton with a 1D 92/93 label placed in the identical position. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton sorts to a store lane | 2D Carton Sorted 1D Carton Sorted | 1 | 1 | 1
Comp_02 | Label Placement Edge compare 2 Process a carton with a 92/93 2D label placed with the label wrapped over the edge of the carton, but all of barcode on one side of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to store lane 1D Carton probably rejects | 2D Sorted 1D Rejected | 1 | 0 | 1
Comp_03 | Label Placement Edge 3 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped vertically over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton rejects 1D Carton rejects | 2D Carton Rejected 1D Carton Rejected | 0 | 0 | 1
Comp_04 | Label Placement Edge 4 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped horizontally over the edge of the carton. Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton rejects 1D Carton rejects | 2D Rejected 1D Rejected | 0 | 0 | 1
Comp_05 | Label Placement Edge 5 Process a carton with a 92/93 2D label placed with the label with 20% of barcode wrapped diagonally over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton rejects 1D Carton rejects | 2D Rejected 1D Rejected | 0 | 0 | 1
Comp_06 | Label Placement Edge 6 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped diagonally over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton rejects 1D Carton rejects | 2D Rejected 1D Rejected | 0 | 0 | 1
Comp_07 | Label Placement crease Process a carton with a 92/93 2D label placed over the centre crease where the box opens (3 cartons with different orientations over the centre crease - ensure that crease is visible in the label) Process a second set of cartons with a 1D 92/93 label placed in the identical position with crease visible on each label | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 6 | As Below | 2D Carton sorts to a store lane 1D Carton rejects sometimes | 1x 2D Label Rejected 2 x 2D sorted 3 x 1D Rejected | 2 | 0 | 3
Comp_08 | Carton corrugations Process a 92/93 2D label on corrugated box. Ensure that wrinkles on the box go through the barcode on the label. Process a second carton with a 1D 92/93 label placed in the similar position with wrinkles in the label | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton does not sort 1D Carton may reject | 2D Label did not sort 1D not run | 0 | 0 | 1
Comp_09 | Crushed carton With a test box, place a 92/93 2D label inducted to the system. Crush the test box such that the label is wrinkles but still readable by the eye, and sort. Process a second carton with a 1D 92/93 label placed in the identical position and crushed in a similar way | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 2 | As Below | 2D Carton may sort to a store lane 1D Carton rejects NB: remove the test cartons wherever they go, and have IT delete the MHS records for them. | No carton found | 0 | 0 | 0
Comp_10 | Tear 1 Tear a corner of the barcode off a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects | 1D Carton Rejected 2D Label sorted | 1 | 0 | 1
Comp_11 | Tear 2 Tear vertically through 1/3rd of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton rejects 1D Carton rejects | 1D Carton Rejected 2D Carton Rejected | 0 | 0 | 1
Comp_12 | Tear 3 Tear vertically through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton rejects | 1D Carton Rejected 2D Carton Rejected | 0 | 0 | 1
Comp_13 | Tear 4 Tear horizontally through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton rejects | 1D Carton Rejected 2D Carton Rejected | 0 | 0 | 1
Comp_14 | Tear 5 Tear diagonally through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton rejects | 1D Carton Rejected 2D Carton Rejected | 0 | 0 | 1
Comp_15 | Poor Print Quality Print a 2D 92/93 label on a printer with poor print quality (unclean or old head) such that some lines print through the barcode and place on a carton and sort Process a second carton with a 1D 92/93 label placed in the identical position and the label printed on the same printer. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton may or may not reject | 2D label sorted 1D failed to sort | 1 | 0 | 1
Comp_16 | Clear tape 1 Process a 2D 92/93 label on a carton where a clear tape obscures one corner of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject | 2D sorted. 1D sorted | 1 | 1 | 1
Comp_17 | Clear tape 2 Process a 2D 92/93 label on a carton where a clear tape obscures 50% of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject | 2D sorted 1D sorted | 1 | 1 | 1
Comp_18 | Clear tape 3 Process a 2D 92/93 label on a carton where a clear tape covers the entire barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort depending on reflections from the tape during the scan. 1D Carton may reject for the same reason. | 2D did not sort - ink leached. 1D did not sort. No ink leach | 0 | 0 | 1
Comp_19 | Kmart tape 1 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 1/4 of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject | 2D did not sort - ink leached. 1D did not sort. No ink leach | 0 | 0 | 1
Comp_20 | Kmart tape 2 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 50% of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may reject | 2D sorted. 1D rejected. | 1 | 0 | 1
Comp_21 | Packing tape 1 Process a 2D 92/93 label on a carton where brown packing tape covers 1/3 of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Fail | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects | 2D did not sort 1D did sort | 0 | 1 | 1
Comp_22 | Packing tape 2 Process a 2D 92/93 label on a carton where brown packing tape covers 50% of the barcode vertically, diagonally, horizontally (3 cartons). Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position.. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 6 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are partially covered) 1D Carton rejects | 2D did not sort x1 2D sorted x2 1D did not sort x2 1D did sorter x 1 | 2 | 1 | 3
Comp_23 | Scuff 1 Place 2D 92/93 label on a carton and lightly scuff the label by dragging the carton with label face down for one metre. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may or may not reject | 2D Sorted 1D did not sort | 1 | 0 | 1
Comp_24 | Scuff 2 Place 2D 92/93 label on a carton and moderately scuff the label by dragging the carton with label face down for one metre and back with small pressure on top of box. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are partially damaged). 1D Carton may or may not reject | 2D sorted 1D sorted | 1 | 1 | 1
Comp_25 | Scuff 3 Place 2D 92/93 label on a carton and heavily scuff the label by dragging the carton with label face down for one metre and back with strong pressure on top of box to grind the label. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are partially damaged). 1D Carton may or may not reject | 2D Sorted 1D Sorted | 1 | 1 | 1
Comp_26 | Offset print Place 2D 92/93 label on a carton where the barcode is printed at the very edge of the label Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position, and also printed with little/no white space at the end of the 92 label. | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton rejects | 2D Sorted 1D Reject | 1 | 0 | 1
[11 empty] | 60 |  |  |  | 15 | 7 | 29
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes |  |  | 51.72% | 24.14%
1 | Prepare cartons with labels as identified in the test. 2D and 1D test cases should be identical | DC Operator/ HO Support | Labels are placed on the cartons as appropriate for the test Photo each carton for the test. |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate Photos should be sent to Head Office (John Herbert) after the test along with the results
2 | Place product for test on to the induction lane(s) for the sorter with all barcodes in scannable positions | DC Operator | Barcode labels can be scanned by the sorter |  |  |  | All labels are in scannable positions
3 | Start sorting the product | Sorter Manager | Sort Director shows the SSCC or shows bad or no read. |  |  |  | Product scans successfully or cannot scan
4 | Product sorts to the appropriate lane for the store or rejects depending on the test. | DC Operator | Product sorts to the appropriate lane for the store allocated by sort director or to the reject lane. Validate that rejects are expected. |  |  |  | Product sorts to the correct store lane or reject lane. Only expected rejects sort to the reject lane. |  |  |  |  | For some tests, the condition of the label will reach a limit where it cannot be scanned.
5 | Count successes and failures | Sorter Manager | Record count of successes and failures Identify SSCC No of failures and note associated picture. |  |  |  | Successes and failures recorded and counted Picture documents the test
6 | Verify sort in option 36 and validate rejects | HO Support | Option 36 shows the SSCC Validate rejected products |  |  |  | SSCC is shown in option 36. Only expected rejects are rejected.
7 | Verify reject cause at reject lane | DC Operator | Use Reject Enquiry to scan rejected cartons to determine the cause of the reject |  |  |  | SSCC scans ok. Reject cause is per the test expection (where appropriate).
8 | Compare counts of successes and failures between 1D and 2D labels | HO Support | Compare successes and rejects for each label type. |  |  |  | 2D labels perform significantly better than their 1D equivalents. |  |  |  |  | Overall result test fails if 1D labels sort more consistently than the 2D labels. Overall result test fails if 1D labels perform about the same as the 2D labels.

## CN80_Standard
Test Name: | Standard CN80 Scan Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Scan_01 | Use scanner to scan a 91 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 91 SSCC is displayed.
CN80Scan_02 | Use scanner to scan a 00 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 00 SSCC is displayed.
CN80Scan_03 | Use scanner to scan the 93 portion of a 1D 92/93 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
CN80Scan_04 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton Use Any | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
CN80Scan_05 | Use scanner to scan a 2D 92/93 SSCC barcode on a polybag Use 43228935 on polybag (should scan but be unlinked to store) | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
CN80Scan_06 | Use scanner to scan a 2D 91 Flow label (None available) | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 91 SSCC is displayed.
CN80Scan_07 | Use scanner to scan a 1D 91 LPN Label (None available) | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 91 SSCC is displayed.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F5=SSCC Enquiry | DC Operator | SSCC Enquiry entry screen displays |  |  |  | SSCC Enquiry Entry screen displays
3 | Scan the SSCC barcode being tested | DC Operator | Ensure that the cursor is at the beginning of the SSCC Enquiry field, and use the CN80 scanner to scan the barcode. |  |  |  | Appropriate 20 long SSCC displays, and shows details of the SCM within 1WMS.

## Consolidation
Test Name: | Standard CN80 Consolidaton Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Cons_01 | Use scanner to consolidate a 2D 93 carton in Non-Cons | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | 93 SSCC is displayed when scanned. 93 SSCC is consolidated to the consolidation.
CN80Cons_02 | Use scanner to consolidate a 2D 93 apparel polybags in apparel area. | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 10 | As Below | 93 SSCC is displayed when scanned. 93 SSCC is consolidated to the consolidation.
RingCons_01 | Use ring scanner to consolidate a 2D 93 carton in Non-Cons | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | See below
RingCons_02 | Use ring scanner to consolidate a 2D 93 apparel polybags in apparel area. | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 10 | As Below | See below
RingCons_03 | Use ring scanner to consolidate a mixture of 1D 92/93 SSCCs and 2D 2D 92/93 SSCCs (mixed 50% or each) | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 10 | As Below | See below
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F3=Consolidation, then F1=Consolidate, then choose the appropriate consolidation option | DC Operator | Consolidation function opens |  |  |  | Consolidation function opens
3 | Enter LA Mode using F7 | DC Operator | LA Mode displays |  |  |  | LA Mode is shown in message area of the RF device
4 | Scan the SSCC | DC Operator | Details of the next store requiring the SSCC are displayed. |  |  |  | SSCC Next Store details displayed |  |  |  |  | NB: This step can be skipped if done for an earlier test
5 | Scan the Consolidation for the Next Store | DC Operator | Consolidation SSCC is entered |  |  |  | Consolidation is displayed |  |  |  |  | NB: This step can be skipped if done for an earlier test
6 | Scan the SSCC being tested | DC Operator | Valiate that 93 SSCC is entered and consolidated. Validate that SSCC count down details are displayed or GO TO Next store details are displayed. |  |  |  | Last SSCC is shown as the just scanned 93 SSCC. X to Go is displayed and/or Go To next store details are displayed |  |  |  |  | If Go To next store , then go there for consolidating the next product.

## CN80_Voice
Test Name: | Standard CN80 Voice Tests | Test All Units | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Voice_01 | Use scanner in voice mode to consolidate a 2D 93 polybag in Apparel area | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 10 | As Below | See below.
CN80Voice_02 | Use scanner in voice mode to consolidate a 1D and 2D 91 polybag in Apparel area | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 10 | As Below | See below.
CN80Voice_03 | Use scanner in voice mode to consolidate a 1D 93 polybag in Apparel area | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 10 | As Below | See below.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Sign on to voice consolidation | DC Operator | Responds with Scan SSCC or Consolidation |  |  |  | SSCC or Consolidation prompt returned
3 | Say "LA Mode" | DC Operator | Responds with "LA Mode, Scan SSCC" |  |  |  | LA Mode, Scan SSCC returned
4 | Scan the test SSCC | DC Operator | Responds with the cluster, next store and the quantity |  |  |  | Cluster nn, Next store nnnn, quantity n |  |  |  |  | NB: This step can be skipped if done for an earlier test
5 | Scan the Consolidation for the Next Store | DC Operator | Responds with the Store number and confirms LA Mode |  |  |  | Store nnnn, LA Mode |  |  |  |  | NB: This step can be skipped if done for an earlier test
6 | Scan the SSCC being tested | DC Operator | Responds with a count down (x to go) May request that you go to another store. |  |  |  | n to go. N to go, go to store nnnn |  |  |  |  | If Go To next store , then go there for consolidating the next product.
7 | After full test confirm SSCCs are consolidated using RF SSCC Enquiry | DC Operator | Validate that the SSCCs show as being resolved to the appropriate store and consolidated |  |  |  | SSCCs do not show as "Not Linked to Store" SSCC status is CO

## Std_Ring_Scan
Test Name: | Standard Ring Scan Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Ring_01 | Use scanner to scan a 91 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
Ring_02 | Use scanner to scan a 00 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
Ring_03 | Use scanner to scan the 93 portion of a 1D 92/93 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
Ring_04 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
Ring_05 | Use scanner to scan a 2D 92/93 SSCC barcode on a polybag | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing. |  |  |  |  | Note: for 92/93 SSCC, use "resolved" SSCCs i.e. ones that are already sorted.
2 | Using Voice, sign on and go to the Enquiry function (one) | DC Operator | Validate that password is accepted Voice prompts to scan the SSCC |  |  |  | Prompts for function, then password Prompt to scan the SSCC |  |  |  |  | Only required first time through
3 | Using the device inbuilt scanner, scan the test SSCC | DC Operator | Validate that the correct store number is returned. |  |  |  | A store number is spoken
4 | Using a paired ring scanner, scan a test SSCC for another store. | DC Operator | Validate that the correct store number is returned. |  |  |  | A store number is spoken

## Vocollect_All
Test Name: | All ring scanner and vocollect tests | [All Ring Scanner devices + All Vocollect Devices] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
RingAll_01 | Use scanner to scan a 91 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
RingAll_02 | Use scanner to scan the 93 portion of a 1D 92/93 SSCC barcode | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
RingAll_03 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | Store number is spoken
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing. |  |  |  |  | Note: for 92/93 SSCC, use "resolved" SSCCs i.e. ones that are already sorted.
2 | Using Voice, sign on and go to the Enquiry function (one) | DC Operator | Validate that password is accepted Voice prompts to scan the SSCC |  |  |  | Prompts for function, then password Prompt to scan the SSCC |  |  |  |  | Only required first time through
3 | Using the device inbuilt scanner, scan the test SSCC | DC Operator | Validate that the correct store number is returned. |  |  |  | A store number is spoken
4 | Using a paired ring scanner, scan a test SSCC for another store. | DC Operator | Validate that the correct store number is returned. |  |  |  | A store number is spoken

## Std_VM1A
Test Name: | Standard Forklift VM1A Scan Tests | [One or two devices during week] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Fork_01 | Use scanner to scan a 91 SSCC barcode | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 91 SSCC is displayed.
Fork_02 | Use scanner to scan a 00 SSCC barcode | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 00 SSCC is displayed.
Fork_03 | Use scanner to scan the 93 portion of a 1D 92/93 SSCC barcode | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
Fork_04 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton | DC Operator | Pre-Work |  |  | Pass | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
Fork_05 | Use scanner to scan a 91 LPN pallet label | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about LPN is displayed.
Fork_06 | Use scanner to scan a 2D 91 SSCC Barcode | DC Operator | Pre-Work |  |  | NA | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about LPN is displayed.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F5=SSCC Enquiry | DC Operator | SSCC Enquiry entry screen displays |  |  |  | SSCC Enquiry Entry screen displays
3 | Scan the SSCC barcode being tested | DC Operator | Ensure that the cursor is at the beginning of the SSCC Enquiry field, and use the CN80 scanner to scan the barcode. |  |  |  | Appropriate 20 long SSCC displays, and shows details of the SCM within 1WMS.

## Cntl Card (hidden)
Test Status
Not executed
In progress
Pass
Fail
Pending
Retest
NA