## Test Summary
2D Label Testing
Test Name | Test Purpose | Comment | DC Team | Head Office Team | Vendor Team | Worksheet Reference | Not executed | In progress | Pass | Fail | Pending | Retest | Total
Pre-Work | Preparation for below tests prior to test day |  | DC Operations | Support |  | #VALUE!
Printer test of 2D barcodes | Testing printing of 1WMS generated 2D barcodes |  | DC Operations | Support |  | #VALUE! | 2 | 0 | 0 | 0 | 0 | 0 | 2
AMR Overhead | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 3 | 0 | 3 | 0 | 0 | 0 | 6
AMR Manual | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 6 | 0 | 0 | 0 | 0 | 0 | 6
AMR Dups | Verify duplicate label heirarchy |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 7 | 0 | 0 | 0 | 0 | 0 | 7
AMR Compare | Verify 2D scan versus 1D scan |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 22 | 0 | 0 | 0 | 0 | 0 | 22
AMR Volume | Volume test of 2D scanning on Sorter |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 1 | 0 | 0 | 0 | 0 | 0 | 1
CN80 Standard | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 1 | 0 | 0 | 0 | 0 | 0 | 1
Consolidaton Tests | Regression test of 1D labels and standard 2D label tests |  | DC Ops, Sorter Manager | Support | Support | #VALUE! | 1 | 0 | 0 | 0 | 0 | 0 | 1
[6 empty] | Total | 43 | 0 | 3 | 0 | 0 | 0 | 46
[6 empty] | Percentage | 93.48% | 0% | 6.522% | 0% | 0% | 0% | 100%

## Pre_Work
Test Sheet | Product Required | Quantity | Comment | Label Source | Label Type
#VALUE! | 92/93 UNRES Pick and Pack in 351 | 3 |  | DC | Generated | =
#VALUE! | 91 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC | 1D 91
#VALUE! | 00 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC | 1D 00
#VALUE! | 1D 92/93 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock | 1D 92/93
#VALUE! | 2D 92/93 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled sortable small sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled sortable large sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled sortable apparel polybag | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled sortable Soft GM polybag | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 91 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC | 2D 91 Flow
#VALUE! | 91 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC | 1D 91
#VALUE! | 00 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC | 1D 00
#VALUE! | 1D 92/93 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock | 1D 92/93
#VALUE! | 2D 92/93 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled sortable polybag | 12 | One per induction point per station. Ensure messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 91 Labelled sortable medium sized carton | 12 | One per induction point per station. Ensure messages are inducted | DC | 2D 91 Flow
#VALUE! | 2 x2D 92/93 Labelled sorter cartons | 12 | 2 of same label applied. Inducted. Per induction station. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 92/93 Labelled carton + 2D label | 12 | Leave 1D label and apply same as 2D on another side. Inducted. Per station. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 1D 92/93 + 2D 92/93
#VALUE! | Replace 92/93 label with 2D + add 2D 91 Flow label | 12 | PnP genuine 92/93 requiring 91 labels. Both inducted i.e another pick with 92/93 label required. Per station. | Replace 92/93 with 2D; Add 91 Label - DC. CBX Generated for 2D for that stock | 2D 92/93 + 2D 91 Flow
#VALUE! | Local 00 labelled stock + 2D label | 12 | Both inducted. 2D label can be random i.e. not for this stock. Per station. | Standard 00 labelled stock, PDF Generated 2D label for other stock from CBX | 1D 00 + 2D 92/93
#VALUE! | Overseas stock with other 00 barcode + 2D label | 12 | 00 barcode not SSCC. Inducted 92/93. Per station. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93 + Other
#VALUE! | 1D 92/93 Labelled carton + 2D label | 12 | 2D label not for this stock, applied on another side. Both inducted. Per station. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 1D 92/93 + 2D 92/93
#VALUE! | 2 x 2D 92/93 Labelled carton. | 12 | 1 x 2D for stock, 1 x 2D for other stock. Both inducted. Per station. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for stock and other stock. | 2D 92/93
#VALUE! | 2D 92/93 labelled cartons - same position as below | 30 | Prepare per test cases, and induct, requires packing tape too. Only test at one station. | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 1D 92/93 labelled cartons - same position as above | 30 | Prepare per test cases, and induct, requires packing tape too. These are twins of the 2D labelled stock, and must be prepared in exactly the same way as the 2D labelled stock for comparison. Test at same station as for 2D labels. | DC Overseas Stock for same products as 2D labelled stock. | 1D 92/93 + 2D 92/93
#VALUE! | 2D 92/93 Labelled sortable cartons | 500 | Ensure that label messages are inducted | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 91 Labelled carton | 1 | Current label | DC | 1D 91
#VALUE! | 00 Labelled carton | 1 | Current label | DC | 1D 00
#VALUE! | 1D 92/93 Labelled carton | 1 | Current label | DC Overseas Stock | 1D 92/93
#VALUE! | 2D 92/93 Labelled carton | 1 | Current label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled polybag | 1 | Current label | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 91 Flow Labelled carton | 1 | Current label | DC | 2D 91 Flow
#VALUE! | 91 labelled Pallet LPN label | 1 | Currently on product Pallet | DC | 1D 91 LPN
#VALUE! | 2D 92/93 Labelled carton | 1 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled apparel polybags | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled apparel polybags | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled carton | 1 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled apparel polybags | 10 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 2D 92/93 Labelled apparel polybags | 5 | Ensure that product is manual mode, test during week | DC Overseas Stock, relabelled with PDF generated CBX 2D labels for that stock | 2D 92/93
#VALUE! | 1D 92/93 Labelled apparel polybags | 5 | Ensure that product is manual mode, test during week, mix with above. | DC Overseas Stock | 1D 92/93
Total Labels |  | 876

## Printers
Test Name: | Printer Test of 2D barcodes | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
Print_1 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Printronix printer. | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 2D Label prints
Print_2 | Re-print a 92/93 pick and pack label (UNRES) as a 2D 92/93 label on a Intermec PC43D printer. | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 2D Label prints
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Go to option 351 | DC Operator | Enters Pick Management |  |  |  | Enters Pick Management
2 | Enter option 7 and find UNRES stock with CC status | DC Operator | Enters Pick Management - SCMs |  |  |  | Enters Pick Management - SCMs
3 | Use option 9=Re-Print | DC Operator | Verify that label is printed from the approprate printer. Validate that the label is a 2D label |  |  |  | 2D label printed

## AMR_Overhead
Test Name: | AMR Overhead | [Test each induction point overhead scanner] | [6 empty] | Test steps are below the test cases |  |  |  | Follow with manual tests
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
AMRO_01 | Sort a 91 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets | Done in normal production
AMRO_02 | Sort a 00 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets | Done in normal production
AMRO_03 | Sort a 1D 92/93 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Pass | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets | Done in normal production
AMRO_04 | Sort a 2D 92/93 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets | No product
AMRO_05 | Sort a 2D 92/93 SSCC labelled small carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRO_06 | Sort a 2D 92/93 SSCC labelled large sortable carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRO_07 | Sort a 2D 92/93 SSCC labelled sortable apparel polybag product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets | No product
AMRO_08 | Sort a 2D 92/93 SSCC labelled sortable soft GM polybag product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | NA | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets | No product
AMRO_09 | Sort a 2D 91 Labelled Flow Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Record product and station on the spreadsheet | DC Operator | Use felt pen to note induction station and left or right induction point being test (12 boxes, one per induction point - can pass per station) |  |  |  | Product recorded |  |  |  |  | This is so that failed cases can be identified. 1D = Linear barcodes 2D = Square barcodes
2 | Place product on to the AMR | DC Operator | Validate correct scanning of the product. Validate that the AMR leaves to a store lane |  |  |  | Product scans successfully Product sorts to the appropriate store lane
3 | Verify sort in option 36 | DC Operator | Option 36 shows the SSCC |  |  |  | SSCC is shown as sorted ok or shows the reject reason |  |  |  |  | Validates that the SSCC information is returned to 1WMS.
Left or Right | Induction Station - Test completion | Pass/Fail
Overhead
Left | STN1L1
Right | STN1L2
Left | STN1U1
Right | STN1U2
Left | STN2L1
Right | STN2L2
Left | STN2U1
Right | STN2U2
Left | STN3L1
Right | STN3L2
Left | STN3U1
Right | STN3U2

## AMR_Manual
Test Name: | AMR Manual | [Test both the left and the right ring scanners at each station] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
AMRM_01 | Sort a 1D 91 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRM_02 | Sort a 00 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRM_03 | Sort a 1D 92/93 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRM_04 | Sort a 2D 92/93 SSCC labelled carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRM_05 | Sort a 2D 92/93 SSCC labelled polybag product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
AMRM_06 | Sort a 2D 91 SSCC labelled medium carton product Test Left and Right at each induction station | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | 1 product per induction point per station (12 altogether. All SSCCs sort to store outlets
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Record product and station on the spreadsheet | DC Operator | Use felt pen to note induction station and left or right induction point being test (12 boxes, one per induction point - can pass per station) |  |  |  | Product recorded |  |  |  |  | This is so that failed cases can be identified. 1D = Linear barcodes 2D = Square barcodes
2 | Place product on to the AMR with barcode facing forwards (to prevent overhead scan - or otherwise block overhead scan) then use left or right ring scanner (one appropriate to the induction point) to scan the barcode. | DC Operator | Validate correct scanning of the product. Validate that the AMR leaves to a store lane |  |  |  | Product scan successfully Product sorts to the appropriate store lane
3 | Verify sort in option 36 | DC Operator | Option 36 shows the SSCC |  |  |  | SSCC is shown as sorted ok or shows the reject reason |  |  |  |  | Validates that the SSCC information is returned to 1WMS.
Left or Right | Induction Station - Test completion | Pass/Fail
Ring Scanner
Left | STN1L1
Right | STN1L2
Left | STN1U1
Right | STN1U2
Left | STN2L1
Right | STN2L2
Left | STN2U1
Right | STN2U2
Left | STN3L1
Right | STN3L2
Left | STN3U1
Right | STN3U2

## AMR_Dups
Test Name: | AMR Priority label tests | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
AMRDup_01 | Process a carton with two 92/93 2D SSCC labels that have the same product and SSCC details | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | Carton sorts to a store outlet
AMRDup_02 | Process a carton with one 1D 92/93 SSCC label and one 92/93 2D SSCC label that have the same product and SSCC details | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | Carton sorts to a store outlet
AMRDup_03 | Process a carton with a 91 label and a 2D 92/93 SSCC label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | Carton sorts to a store outlet based on the 91 label
AMRDup_04 | Process a carton with a sortable 00 label known to the sorter and a 2D 92/93 label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | AMR waits for the correct SSCC to be scanned.
AMRDup_05 | Process a carton with a 00 description (non-SSCC) barcode and a 2D 92/93 label (if carton available for this) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | Carton sorts to a store lane based on the 92/93 label
AMRDup_06 | Process a carton with a 1D 92/93 SSCC and a 2D 92/93 with different products encoded in the labels (different 92). | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | AMR waits for the correct SSCC to be scanned.
AMRDup_07 | Process a carton with two 2D SSCC labels that have different products encoded (different 92 SSCCs). One 2D label should be for the product in the box. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 12 | As Below | AMR waits for the correct SSCC to be scanned.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare cartons with labels as identified in the test | DC Operator/ HO Support | Labels are placed on the cartons |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate
2 | Place product on to the AMR | DC Operator | Validate correct scanning of the product. Validate that the AMR leaves to a store or induction station indicates that the correct label needs to be scanned due to the priority conflict. |  |  |  | Product scans successfully or AMR remains in place until the appropriate barcode is hand scanned or the product is Jackpot rejected Product sorts to the appropriate store outlet or reject outlet
3 | Verify sort in option 36 and validate rejects | HO Support | Option 36 shows the SSCC Validate rejected products |  |  |  | SSCC is shown in option 36. Only expected rejects are rejected.

## AMR_Compare
Test Name: | AMR Bad Label Comparison | [These tests need to be done at one station] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  | Likely Result | Results (Please fill in and return to John) |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps |  | 1D Label (0=Reject, 1 or greater = Pass) | 2D Label (0=Reject, 1 or greater = Pass) | Test Count per label type | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
AMRComp_01 | Label Placement Edge compare 1 Process a carton with a 92/93 2D label placed with the full label at the edge of the carton. Process a second carton with a 1D 92/93 label placed in the identical position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton sorts to a store lane |  |  | 1
AMRComp_02 | Label Placement Edge compare 2 Process a carton with a 92/93 2D label placed with the label wrapped over the edge of the carton, but all of barcode on one side of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton probably rejects |  |  | 1
AMRComp_03 | Label Placement Edge 3 Process a carton with a 92/93 2D label placed with the label with 50% of barcode wrapped vertically over the edge of the carton Process a second carton with a 1D 92/93 label placed in the identical position | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton rejects 1D Carton rejects |  |  | 1
AMRComp_04 | Label Placement crease Process a carton with a 92/93 2D label placed over the centre crease where the box opens (3 cartons with different orientations over the centre crease - ensure that crease is visible in the label) Process a second set of cartons with a 1D 92/93 label placed in the identical position with crease visible on each label | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 6 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may or may not sort to a store lane |  |  | 3
AMRComp_05 | Carton corrugations Process a 92/93 2D label on corrugated box. Ensure that wrinkles on the box go through the barcode on the label. Process a second carton with a 1D 92/93 label placed in the similar position with wrinkles in the label (if a carton is available) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may or may not sort to a store lane |  |  | 1
AMRComp_06 | Crushed carton With a test box, place a 92/93 2D label inducted to the system. Crush the test box such that the label is wrinkles but still readable by the eye, and sort. Process a second carton with a 1D 92/93 label placed in the identical position and crushed in a similar way (if carton is available) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may or may not sort to a store lane. |  |  | 1
AMRComp_07 | Tear 1 Tear a small corner of the barcode off a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton rejects |  |  | 1
AMRComp_08 | Tear 2 Tear vertically through 1/3rd of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton rejects |  |  | 1
AMRComp_09 | Tear 3 Tear vertically through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. [Note that the four squares are not independent copies - so damaging any one may cause a reject, or may be covered by error correction). 1D Carton rejects |  |  | 1
AMRComp_10 | Tear 4 Tear horizontally through 50% of the barcode on a 92/93 2D label and place on a carton and sort. Process a second carton with a 1D 92/93 label placed in the identical position and with the same tear through the barcode | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. 1D Carton rejects |  |  | 1
AMRComp_11 | Poor Print Quality Print a 2D 92/93 label on a printer with poor print quality (unclean or old head) such that some lines print through the barcode and place on a carton and sort Process a second carton with a 1D 92/93 label placed in the identical position and the label printed on the same printer. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (depends if all four squares are damaged) 1D Carton may or may not reject |  |  | 1
AMRComp_12 | Clear tape 1 Process a 2D 92/93 label on a carton where a clear tape obscures one corner of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may reject |  |  | 1
AMRComp_13 | Clear tape 2 Process a 2D 92/93 label on a carton where a clear tape obscures 50% of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may reject |  |  | 1
AMRComp_14 | Clear tape 3 Process a 2D 92/93 label on a carton where a clear tape covers the entire barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort depending on reflections from the tape during the scan. 1D Carton may reject for the same reason. |  |  | 1
AMRComp_15 | Kmart tape 1 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 1/4 of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. (can use red felt pen on the label to emulate Anko labels) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may reject |  |  | 1
AMRComp_16 | Kmart tape 2 Process a 2D 92/93 label on a carton where red and clear "kmart" tape covers 50% of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to a store lane 1D Carton may reject |  |  | 1
AMRComp_17 | Packing tape 1 Process a 2D 92/93 label on a carton where brown packing tape covers 1/3 of the barcode. Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort depending on coverage and whether scanner reads through the tape 1D same |  |  | 1
AMRComp_18 | Packing tape 2 Process a 2D 92/93 label on a carton where brown packing tape covers 50% of the barcode vertically, diagonally, horizontally (3 cartons). Process a second carton with a 1D 92/93 label placed in the identical position with tape in the same position.. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 6 | As Below | 2D Carton may or may not sort depending on coverage and whether scanner reads through the tape 1D same |  |  | 3
AMRComp_19 | Scuff 1 Place 2D 92/93 label on a carton and lightly scuff the label by dragging the carton with label face down for one metre. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane 1D Carton may or may not reject |  |  | 1
AMRComp_20 | Scuff 2 Place 2D 92/93 label on a carton and moderately scuff the label by dragging the carton with label face down for one metre and back with small pressure on top of box. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. . 1D Carton may or may not reject |  |  | 1
AMRComp_21 | Scuff 3 Place 2D 92/93 label on a carton and heavily scuff the label by dragging the carton with label face down for one metre and back with strong pressure on top of box to grind the label. Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position and scuffed using the same process. | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton may or may not sort to store. (It sorted during Truganina trial) 1D Carton may or may not reject |  |  | 1
AMRComp_22 | Offset print Place 2D 92/93 label on a carton where the barcode is printed at the very edge of the label Process on sorter. Process a second carton with a 1D 92/93 label placed in the identical position, and also printed with little/no white space at the end of the 92 label. (can emulate this by cutting off white space next to the barcode in both cases) | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 2 | As Below | 2D Carton sorts to a store lane (so long as the label is not otherwise damaged) 1D Carton rejects (due to lack of white space) |  |  | 1
[11 empty] | 52 |  |  | 0 | 0 | 26
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare cartons with labels as identified in the test | DC Operator/ HO Support | Labels are placed on the cartons as appropriate for the test Photo each carton for the test. |  |  |  | Cartons are ready for the test |  |  |  |  | Ensure that product is sortable and in the sorter tables where appropriate Photos should be sent to Head Office (John Herbert) after the test along with the results
1 | Place product on to the AMR | DC Operator | Validate correct scanning of the product. Validate that the AMR leaves to a store without using the ring scanner, |  |  |  | Product scans successfully or AMR remains in place.
1 | Count successes and failures | Sorter Manager | Record count of successes and failures Identify SSCC No of failures and note associated picture. |  |  |  | Successes and failures recorded for overhead scan and counted Picture documents the test
1 | For product where the AMR did not leave, attempt to scan the barcodes with the hand scanner. | DC Operator | Validate that after ring scan, that product goes to a store outlet. If the barcode is not registered, scan the jackpot reject. |  |  |  | Product scans successfully or AMR is sent to the jackpot reject.
1 | Count successes and failures after hand scan if required (note that it was a hand (ring scanner) scan. | Sorter Manager | Record count of successes and failures Identify SSCC No of failures and note associated picture. |  |  |  | Successes and failures recorded for hand scan and counted Picture documents the test
1 | Compare counts of successes and failures between 1D and 2D labels, overhead vs ring scanner. | HO Support | Compare successes and failures for each label type by type of scan. |  |  |  | 2D labels perform significantly better than their 1D equivalents. |  |  |  |  | Overall result test fails if 1D labels sort more consistently than the 2D labels. Overall result test fails if 1D labels perform about the same as the 2D labels.
It is hoped that 2D barocdes have a greater overall score at the end of the test compared to 1D labels. At Truganina, this was the case.

## AMR_Volume
Test Name: | AMR Volume Rates | [7 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
AMRVol_01 | Process 500+ 2D labelled cartons | DC Operator | Pre-Work |  |  | Not executed | N/A | Any | Any | Any | 500 | As Below | 2D Sort ok to store outlets. Any that reject should have a good reason other than not readable (e.g. No_Demand). None should go to the Jackpot Reject due to being unreadable.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Prepare 500 cartons with labels as required by the test | DC Operator/ HO Support | 500 cartons prepared for the test with labels applied Product data is inducted to the sorter |  |  |  | 500 cartons per test with 2D labels prepared |  |  |  |  | Ensure that all product it is sortable and has fresh messages on the sorter.
2 | Place product on to the AMR | DC Operator | Validate correct scanning of the product. Validate that the AMR leaves to a store without using the ring scanner. |  |  |  | Product scans successfully.
3 | Product sorts to the appropriate outlet for the store | DC Operator | Product sorts to the appropriate outlet for the store allocated by tWes |  |  |  | Product sorts to the correct store outlet
4 | Verify sort in option 36 and extract data | HO Support | Option 36 shows the SSCC Extract sorter data and verify all sorted ok. |  |  |  | SSCC is shown as sorted ok |  |  |  |  | Check for any rejects, and check causes. Test fails if there are 2D barcode read failures when scanned.

## CN80_Standard
Test Name: | Standard CN80 Scan Tests | [One or two devices] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Scan_01 | Use scanner to scan a 2D 92/93 SSCC barcode on a carton | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | SSCC scans properly. SSCC Enquiry information about the 93 SSCC is displayed.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F5=SSCC Enquiry | DC Operator | SSCC Enquiry entry screen displays |  |  |  | SSCC Enquiry Entry screen displays
3 | Scan the SSCC barcode being tested | DC Operator | Ensure that the cursor is at the beginning of the SSCC Enquiry field, and use the CN80 scanner to scan the barcode. |  |  |  | Appropriate 20 long SSCC displays, and shows details of the SCM within 1WMS.

## Consolidation
Test Name: | Standard CN80 Consolidaton Tests | [One or two devices] | [6 empty] | Test steps are below the test cases
[7 empty] | Sortation Attributes |  |  | Test Data |  |  |  |  | Results |  |  | Record Details before testing
Test ID | Test Scenarios | Who | Dependency | Assigned To | Date | Status | Product Type | PO# | Pick # | Keycode | Store / Qty | Test Steps | Expected Result | Expected Lane ID Sorted To | Sort Lane | SSCC | Actual Result | Special Features of the product | Barcode/s
CN80Cons_01 | Use scanner to consolidate a 2D 93 carton in Non-Cons | DC Operator | Pre-Work |  |  | Not executed | N/A |  | Any |  | 1 | As Below | 93 SSCC is displayed when scanned. 93 SSCC is consolidated to the consolidation.
Test Step # | Test Step | Who | Validation Step |  |  |  | Expected Result |  |  |  |  | Notes
1 | Obtain product with appropriate labels, or relabel as necessary. | DC Operator | Appropriately labelled product is available |  |  |  | Product with appropriate labels applied is available for processing.
2 | Enter RF option F3=Consolidation, then F1=Consolidate, then choose the appropriate consolidation option | DC Operator | Consolidation function opens |  |  |  | Consolidation function opens
3 | Enter LA Mode using F7 | DC Operator | LA Mode displays |  |  |  | LA Mode is shown in message area of the RF device
4 | Scan the SSCC | DC Operator | Details of the next store requiring the SSCC are displayed. |  |  |  | SSCC Next Store details displayed |  |  |  |  | NB: This step can be skipped if done for an earlier test
5 | Scan the Consolidation for the Next Store | DC Operator | Consolidation SSCC is entered |  |  |  | Consolidation is displayed |  |  |  |  | NB: This step can be skipped if done for an earlier test
6 | Scan the SSCC being tested | DC Operator | Valiate that 93 SSCC is entered and consolidated. Validate that SSCC count down details are displayed or GO TO Next store details are displayed. |  |  |  | Last SSCC is shown as the just scanned 93 SSCC. X to Go is displayed and/or Go To next store details are displayed |  |  |  |  | If Go To next store , then go there for consolidating the next product.

## Cntl Card (hidden)
Test Status
Not executed
In progress
Pass
Fail
Pending
Retest
NA