## Australia
# | Test Area | Top Level Test Name | Phase | Lead | Detail Test Sheet Reference | Individual test est. timing (minutes) | No. of Tests | No. of Ops Team People | No. of HO People | No. of vendor people | Total Time per Person (minutes) | On Site | Test Day |  |  |  | Minutes in a day
DC Printer Test
1 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on Printronix | SIT, PVT | Head Office | 01 PVT Dematic Sorter - Printers - Print-01 | 10 | 1 | 1 |  |  | 10 | DC Operations | Bus. Day | 1 | 60 | 8 | 480
2 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on Intermec PC43D printers | SIT, PVT | Head Office | 01 PVT Dematic Sorter - Printers - Print-02 | 10 | 1 | 1 |  |  | 10 | DC Operations | Bus. Day
3 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on intermec PB50 printers | SIT, PVT | Head Office | 01 PVT Dematic Sorter - Printers - Print-03 | 10 | 1 | 1 |  |  | 10 | DC Operations | Bus. Day
| Dematic Sorter | Prepwork required during week before test
4 | Dematic Sorter | Standard carton 1D 91 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-01 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
5 | Dematic Sorter | Standard carton 1D 00 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-02 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
6 | Dematic Sorter | Standard carton 1D 92/93 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-03 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
7 | Dematic Sorter | Standard carton 2D 92/93 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-04 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
8 | Dematic Sorter | Small carton 2D 92/93 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-05 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
9 | Dematic Sorter | Large carton 2D 92/93 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-06 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
10 | Dematic Sorter | Polybag 2D 92/93 label test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Standard - Sort-07 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
11 | Dematic Sorter | Clean 2D 92/93 label volume test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Volume - Vol-01 | 120 | 1 | 4 | 1 | 1 | 30 | DC Ops, HO, Dem | Weekend
12 | Dematic Sorter | Normal stock 1D 92/93 and mixed 2D 92/93 labels sorting test with volume | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Volume - Vol-02 | 120 | 1 | 4 | 1 | 1 | 30 | DC Ops, HO, Dem | Weekend
13 | Dematic Sorter | Duplicate 2D 92/93 SSCCs of same type on carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-01 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
14 | Dematic Sorter | Duplicate 1D 92/93 and 2D 92/93 SSCC of same type on carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-02 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
15 | Dematic Sorter | Priority conflict 1D 91 label with 2D 92/93 SSCC on same carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-03 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
16 | Dematic Sorter | Priority conflict 1D 00 label (known to sorter) with 2D 92/93 SSCC on same carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-04 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
17 | Dematic Sorter | Priority conflict 1D 00 label (unknown to sorter) with 2D 92/93 SSCC on same carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-05 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
18 | Dematic Sorter | Priority conflict 1D 92/93 and 2D 92/93 with different SSCCs on same carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-06 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
19 | Dematic Sorter | Priority conflict 2D 92/93 and 2D 92/93 with different SSCCs on same carton | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Dups - Dup-07 | 10 | 1 | 1 | 1 | 1 | 10 | DC Ops, HO, Dem | Weekend
20 | Dematic Sorter | Specific 2D sub optimal label limit test | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Bad Label - 26 test cases | 60 | 1 | 1 | 1 | 1 | 60 | DC Ops, HO, Dem | Weekend
21 | Dematic Sorter | Specific 2D sub optimal label comparison tests with 1D 92/93 labels with same conditions | PVT | Head Office | 01 PVT Dematic Sorter - Sorter Comparison - 26 test cases | 90 | 1 | 1 | 1 | 1 | 90 | DC Ops, HO, Dem | Weekend
| CN80 Scanner | Prepwork required during week before test
22 | CN80 Scanner | Standard carton 1D 91 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
23 | CN80 Scanner | Standard carton 1D 00 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
24 | CN80 Scanner | Standard carton 1D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
25 | CN80 Scanner | Standard carton 2D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
26 | CN80 Scanner | Polybag 2D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
28 | CN80 Scanner | Non-Cons carton 2D consolidation test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Consolidation - CN80Cons_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
27 | CN80 Scanner | Polybag mixed 1D and 2D 92/93 apparel consolidation test at volume (speed) | PVT | Head Office | 02 PVT CN80 Scanner - Consolidation - CN80Cons_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
29 | CN80 Scanner | Voice consolidation of polybags with 2D labels | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Voice - CN80Voice_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
30 | CN80 Scanner | All CN80 Scanners validation test with 1D and 2D SSCC using SSCC Enquiry or Reject Enquiry. | PVT | Head Office | 02 PVT CN80 Scanner - CN80 All - 3 tests per device | 10 | 100 | 10 | 1 | 1 | 100 | DC Ops, HO, Korb | Weekend
| Voice Ring Scanner | Prepwork required during week before test
31 | Voice Ring Scanner | Standard carton 1D 91 label SSCC Enquiry test with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
32 | Voice Ring Scanner | Standard carton 1D 00 label SSCC Enquiry test with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
33 | Voice Ring Scanner | Standard carton 1D 92/93 label SSCC Enquiry test with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
34 | Voice Ring Scanner | Standard carton 2D 92/93 label SSCC Enquiry test with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
35 | Voice Ring Scanner | Polybag 2D 92/93 label SSCC Enquiry test with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
36 | Voice Ring Scanner | Non-Cons carton 2D consolidation test with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Consolidation - RingCons_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
37 | Voice Ring Scanner | Voice consolidation of polybags with 2D labels with vocollect and CN80 | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Consolidation - RingCons_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
38 | Voice Ring Scanner | Polybag mixed voice 1D and 2D 92/93 apparel consolidation test at volume (speed) with vocollect and CN80 | PVT | Head Office | 03 PVT Voice Ring Scanner - Consolidation - RingCons_03 | 15 | 1 | 1 |  |  | 15 | DC Ops | Bus. Day
39 | Voice Ring Scanner | All ring scanner validation test of 1D and 2D labels with linked devices (incl. Vocollect scanner) | PVT | Head Office | 03 PVT Voice Ring Scanner - Ring and Vocollect All - 3 tests per device | 10 | 100 | 10 | 1 | 1 | 100 | DC Ops, HO, Korb | Weekend
| VM1A Forklift Scanners | Prepwork required during week before test
40 | Forklift Scanners | Standard carton 1D 91 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
41 | Forklift Scanners | Standard carton 1D 00 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
42 | Forklift Scanners | Standard carton 1D 92/93 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
43 | Forklift Scanners | Standard carton 2D 92/93 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
44 | Forklift Scanners | Task LPN Label scan test (LPN Enquiry) | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
45 | Forklift Scanners | All Forklift Scanners of 1D and 2D SSCC tests using SSCC Enquiry | PVT | Head Office | 04 PVT Forklift Scanner - Fork All - 3 tests per device | 10 | 20 | 5 | 1 | 1 | 40 | DC Ops, HO, Korb | Weekend
Honeywell Xenon XP scanners (replacement to Cino scanners)
46 | Xenon XP | Standard carton 1D 91 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
47 | Xenon XP | Standard carton 1D 00 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
48 | Xenon XP | Standard carton 1D 92/93 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
49 | Xenon XP | Standard carton 2D 92/93 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day

## NZ Wiri
# | Test Area | Top Level Test Name | Phase | Lead | Detail Test Sheet Reference | Individual test timing (minutes) | No. of Tests | No. of Ops Team People | No. of HO People | No. of vendor people | Total Time per Person (minutes) | On Site | Test Day |  |  |  | Minutes in a day
DC Printer Test
1 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on Printronix | SIT, PVT | Head Office | 06 PVT Tompkins Sorter - Printers - Print-01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day | 1 | 60 | 8 | 480
2 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on Intermec PC43D printers | SIT, PVT | Head Office | 06 PVT Tompkins Sorter - Printers - Print-02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
3 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on intermec PB50 printers | SIT, PVT | Head Office | 06 PVT Tompkins Sorter - Printers - Print-03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
| Tompkins Sorter | Prepwork required during week before test
4 | Tompkins Sorter | Standard carton 1D 91 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_01 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
5 | Tompkins Sorter | Standard carton 1D 00 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_02 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
6 | Tompkins Sorter | Standard carton 1D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_03 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
7 | Tompkins Sorter | Standard carton 2D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_04 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
8 | Tompkins Sorter | Small carton 2D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_05 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
9 | Tompkins Sorter | Large carton 2D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_06 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
10 | Tompkins Sorter | Polybag apparel 2D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_07 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
11 | Tompkins Sorter | Polybag soft GM 2D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Overhead - AMRO_08 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
12 | Tompkins Sorter | Left and Right ring scanner 1D 91 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Manual - AMRM_01 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
13 | Tompkins Sorter | Left and Right ring scanner 1D 00 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Manual - AMRM_02 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
14 | Tompkins Sorter | Left and Right ring scanner 1D 92/93 label test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Manual - AMRM_03 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
15 | Tompkins Sorter | Left and Right ring scanner 2D 92/93 label on carton test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Manual - AMRM_04 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
16 | Tompkins Sorter | Left and Right ring scanner 2D 92/93 label on polybag test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Manual - AMRM_05 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
17 | Tompkins Sorter | Duplicate 2D 92/93 SSCCs of same type on carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_01 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
18 | Tompkins Sorter | Duplicate 1D 92/93 and 2D 92/93 SSCC of same type on carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_02 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
19 | Tompkins Sorter | Priority conflict 1D 91 label with 2D 92/93 SSCC on same carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_03 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
20 | Tompkins Sorter | Priority conflict 1D 00 label (known to sorter) with 2D 92/93 SSCC on same carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_04 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
21 | Tompkins Sorter | Priority conflict 1D 00 label (unknown to sorter) with 2D 92/93 SSCC on same carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_05 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
22 | Tompkins Sorter | Priority conflict 1D 92/93 and 2D 92/93 with different SSCCs on same carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_06 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
23 | Tompkins Sorter | Priority conflict 2D 92/93 and 2D 92/93 with different SSCCs on same carton per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Dups - AMRDup_07 | 30 | 1 | 3 | 1 | 1 | 10 | DC Ops, HO, Dem, Tom remote | Weekend
24 | Tompkins Sorter | Specific 2D sub optimal label limit test at one station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Bad Label - 26 tests | 60 | 1 | 1 | 1 | 1 | 60 | DC Ops, HO, Dem, Tom remote | Weekend
25 | Tompkins Sorter | Specific 2D sub optimal label comparison tests with 1D 92/93 labels with same conditions at one station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Bad Compare - 26 tests | 90 | 1 | 1 | 1 | 1 | 90 | DC Ops, HO, Dem, Tom remote | Weekend
26 | Tompkins Sorter | Clean 2D 92/93 label volume test per station | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Volume - AMRVol_01 | 120 | 1 | 4 | 1 | 1 | 30 | DC Ops, HO, Dem, Tom remote | Weekend
27 | Tompkins Sorter | Normal stock 1D 92/93 and mixed 2D 92/93 labels sorting test with volume | PVT | Head Office | 06 PVT Tompkins Sorter - AMR Volume - AMRVol_02 | 120 | 1 | 4 | 1 | 1 | 30 | DC Ops, HO, Dem, Tom remote | Weekend
| CN80 Scanner | Prepwork required during week before test
28 | CN80 Scanner | Standard carton 1D 91 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
29 | CN80 Scanner | Standard carton 1D 00 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
30 | CN80 Scanner | Standard carton 1D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
31 | CN80 Scanner | Standard carton 2D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
32 | CN80 Scanner | Polybag 2D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
33 | CN80 Scanner | Non-Cons carton 2D consolidation test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Consolidation - CN80Cons_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
34 | CN80 Scanner | tWes Close out scanner test | PVT | Head Office | 02 PVT CN80 Scanner - NZ Wiri Closeout - Close_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
35 | CN80 Scanner | All CN80 Scanners validation test with 1D and 2D SSCC using SSCC Enquiry or Reject Enquiry and close out scanning | PVT | Head Office | 02 PVT CN80 Scanner - CN80 All - 3 tests per device + Closeout test | 10 | 100 | 10 | 1 | 1 | 100 | DC Ops, HO, Korb | Weekend
| VM1A Forklift Scanners | Prepwork required during week before test
36 | Forklift Scanners | Standard carton 1D 91 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
37 | Forklift Scanners | Standard carton 1D 00 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
38 | Forklift Scanners | Standard carton 1D 92/93 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
39 | Forklift Scanners | Standard carton 2D 92/93 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
40 | Forklift Scanners | Task LPN Label scan test (LPN Enquiry) | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
41 | Forklift Scanners | All Forklift Scanners of 1D and 2D SSCC tests using SSCC Enquiry | PVT | Head Office | 04 PVT Forklift Scanner - Fork All - 3 tests per device | 10 | 20 | 5 | 1 | 1 | 40 | DC Ops, HO, Korb | Weekend
Honeywell Xenon XP scanners (replacement to Cino scanners)
42 | Xenon XP | Standard carton 1D 91 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
43 | Xenon XP | Standard carton 1D 00 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
44 | Xenon XP | Standard carton 1D 92/93 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
45 | Xenon XP | Standard carton 2D 92/93 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day

## NZ CHCH
# | Test Area | Top Level Test Name | Phase | Lead | Detail Test Sheet Reference | Individual test timing (minutes) | No. of Tests | No. of Ops Team People | No. of HO People | No. of vendor people | Total Time per Person (minutes) | On Site | Test Day |  |  |  | Minutes in a day
DC Printer Test
1 | DC Printer Test | Re-print existing SSCCs as 2D 92/93 labels on Printronix | SIT, PVT | Head Office | 01 PVT Dematic Sorter - Printers - Print-01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day | 1 | 60 | 8 | 480
| CN80 Scanner | Prepwork required during week before test
4 | CN80 Scanner | Standard carton 1D 91 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
5 | CN80 Scanner | Standard carton 1D 00 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
6 | CN80 Scanner | Standard carton 1D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
7 | CN80 Scanner | Standard carton 2D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
8 | CN80 Scanner | Polybag 2D 92/93 label SSCC Enquiry test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Standard Scan - CN80Scan_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
9 | CN80 Scanner | Non-Cons carton 2D consolidation test | SIT, PVT | Head Office | 02 PVT CN80 Scanner - Consolidation - CN80Cons_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
10 | CN80 Scanner | All CN80 Scanners validation test with 1D and 2D SSCC using SSCC Enquiry or Reject Enquiry. | PVT | Head Office | 02 PVT CN80 Scanner - CN80 All - 3 tests per device | 10 | 100 | 10 |  |  | 100 | DC Ops | Weekend
| Voice Ring Scanner | Prepwork required during week before test
11 | Voice Ring Scanner | Standard carton 1D 91 label SSCC Enquiry test with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
12 | Voice Ring Scanner | Standard carton 1D 00 label SSCC Enquiry test with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
13 | Voice Ring Scanner | Standard carton 1D 92/93 label SSCC Enquiry test with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
14 | Voice Ring Scanner | Standard carton 2D 92/93 label SSCC Enquiry test with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
15 | Voice Ring Scanner | Polybag 2D 92/93 label SSCC Enquiry test with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Standard Scan - Ring_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
16 | Voice Ring Scanner | Non-Cons carton 2D consolidation test with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Consolidation - RingCons_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
17 | Voice Ring Scanner | Voice consolidation of polybags with 2D labels with vocollect | SIT, PVT | Head Office | 03 PVT Voice Ring Scanner - Consolidation - RingCons_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
18 | Voice Ring Scanner | All ring scanner validation test of 1D and 2D labels with linked devices (incl. Vocollect scanner) | PVT | Head Office | 03 PVT Voice Ring Scanner - Ring and Vocollect All - 3 tests per device | 10 | 100 | 10 |  |  | 100 | DC Ops | Weekend
| VM1A Forklift Scanners | Prepwork required during week before test
19 | Forklift Scanners | Standard carton 1D 91 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
20 | Forklift Scanners | Standard carton 1D 00 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
21 | Forklift Scanners | Standard carton 1D 92/93 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
22 | Forklift Scanners | Standard carton 2D 92/93 label SSCC Enquiry test with SSCC Enquiry | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
23 | Forklift Scanners | Task LPN Label scan test (LPN Enquiry) | SIT, PVT | Head Office | 04 PVT Forklift Scanner - Standard Scan - Fork_05 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
24 | Forklift Scanners | All Forklift Scanners of 1D and 2D SSCC tests using SSCC Enquiry | PVT | Head Office | 04 PVT Forklift Scanner - Fork All - 3 tests per device | 10 | 20 | 5 |  |  | 40 | DC Ops | Weekend
Honeywell Xenon XP scanners (replacement to Cino scanners)
25 | Xenon XP | Standard carton 1D 91 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_01 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
26 | Xenon XP | Standard carton 1D 00 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_02 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
27 | Xenon XP | Standard carton 1D 92/93 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_03 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day
28 | Xenon XP | Standard carton 2D 92/93 label SSCC Enquiry test with SCM Enquiry | SIT, PVT | Head Office | 05 PVT Xenon - Xenon All - Xenon_04 | 10 | 1 | 1 |  |  | 10 | DC Ops | Bus. Day